## Front Page
Return to Main Menu
Return to Main Menu
Board Assurance Framework
2022 - 23

## Quality & Patient Experience
Risk Theme: Quality & Patient Experience
RISK APPETITE: MINIMALIST - Upper tolerance limit 6
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO6: Population Health
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF1 Failure to maintain safety and quality and avoid harm would result in poorer patient & family experience Executive Risk Lead: Sue Pemberton, Director of Nursing and Quality Board Committee: Quality Committee Last Update: 14 March 2023 | Causes - Covid part of the long-term operating context - Population health needs change due to long-term effects of Covid - Further surges / new variants - Insufficient workforce capacity - Staff wellbeing - Nosocomial outbreaks - Change from open visiting to more restricted times - Patients may present more clinically unwell due to longer waiting times - A higher proportion of patients with psychological/mental health issues post covid Consequences - Poorer patient experience - Less favourable patient outcomes - Ability to maintain CQC ‘outstanding’ - Patients not treated promptly and within waiting time targets - Deterioration in positive feedback from patients and families and negative patient survey results - Failure to implement the principles from the national safety strategy | 5 x 4 = 20 | C1) The quality and safety strategy 2021/24 sets out the workstreams to ensure the hosiptal delivers high quality and safe care. Control Owner: Sue Pemberton | IPC BAF Quarterly reports and incident reports to the Board of Directors. Quality strategy progress reports to Quality Committee. Quality dashboard to Qualtiy Committee and KPIs to Board of Directors. Learning from external reviews (e.g. Ockenden, Edenfield). | National inpatient survey results | Acceptable | 3 x 2 = 6 | YES | Implementation of new patient safety framework. | To implement the new patient safety framework across the Trust. Action Owner: Sue Pemberton Due date: Further update April 2023 | Quality strategy progress reports now established. Patient Safety Icident Response Framework implementation plan developed. New Patient Safety Lead appointed and patient safety champions recruited. Patient Safety Partners appointed. Safety walkabouts taking place. | 3 x 2 = 6 | 2023-03-01
|  |  | C2) Infection Prevention BAF sets out the priorities being implemented to improve performance. Control Owner: Raph Perry | IPC BAF reports to the Board of Directors. | CQC reports and rating | Acceptable
|  |  | C3) EECS and CQC mock inspections process. Control Owner: Sue Pemberton | IICC report 6/12 and complaints reports anuually. EECS and internal CQC mock assessments reported to Board. | Commissioner reviews of quality (quarterly) | Acceptable
|  |  | C4)The organisational learning plan for the Trust supports improvements in practice and care for patients. Control Owner: Karan Wheatcroft | Organisation learning reported through various forums including Operational Board and via QSEC to Quality Committee. Board of Directors receives ICCI reports and learning from deaths updates (quarterly). Organisational learning strategy approved by Board through CGM. | GIRFT reports and associated action plans | Partial |  |  | Failure to embed the learning from incidents could impact on patient safety and quality. | Develop trust wide learning plan and roll out learning database. Action Owner: Karan Wheatcroft Due Date: Further update Jan 2023 | Organisational learning database developed bringing together all the Trust learning to assess themes and take action. Launched with Divisions and further refinement in progress including learning from mortality reviews prior to wider roll .
|  |  | C5) Quality Governance Structure - QSEC, and Quality Committee. Control Owner: Sue Pemberton | QIA process for CIP reporting through Quality Committee. Quality dashboard reporting through Quality Committee and KPIs to Board. Annual review of Committee effectiveness. Clinical policies and guidelines approved through governance structure. Quality Committee BAF key issues report. National and local audits reported through CAEG. | CQC Insight report to Board of Directors twice yearly. | Acceptable |  |  | CQC are revising their strategy therefore there may be changes to their inspection criteria. | Keep abreast of changes to the CQC strategy and embed into the trusts EECS process as required. Action owner: Sue Pemberton Due Date: Further update April 2023 | EECS and internal CQC mock assessment in place. Also actively learning from other CQC inspections. Regular contact maintained with the CQC through relationship meetings.
|  |  | C6) Review of deaths Control Owner: Raph Perry | Mortality improvement group reporting through the Quality Committee. Medical examiners. Mortality review group. | Dr Foster benchmarking | Acceptable |  |  |  | Completion of divisional mortality improvement plan and continued improvements tracked through the Mortlity Improvement Group. Action owner: Raph Perry Due Date:Further update April 2023 | Mortality improvement plan progress update reported to the Board shows significant progress against the planned actions. Telstra Health update for Board in Sept 2022. The Mortality Improvement Group continues to operate and HSMR has been within expected range for 6 months. Divisional mortality improvement plans are complete with the exception of longer term actions. New leadership for MRG and invovlement from Patient Safety Lead with a focus on learning.
Return to Main Menu
Return to Main Menu

## Operational Effectiveness
Risk Theme: Operational Effectiveness
RISK APPETITE: CAUTIOUS - Upper tolerance limit 9
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO6: Population Health
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF2 Inability to recover operational services in line with 22/23 planning guidance could result in poorer patient outcomes, inability to address the backlog of patients waiting and deliver financial consequences to the Trust Executive Risk Lead: Jonathan Mathews, Chief Operating Officer Board Committee: Integrated Performance Committee Last Update: 14th March 2023 | Causes - Insufficient workforce capacity to provide more than pre-Covid levels of activity - Unmet demand that did not present / get referred to services during the height of the pandemic, leading to a significant increase in the waiting list, above core funded capacity - Further surges / new variants - Backlog patients’ conditions have worsened while waiting - Pressures of mutual aid requirement based on system priorities Consequences - Inability to meet statutory waiting list / access targets - Failing to acheive SOF level 1 - Poorer patient outcomes and experience with extending waiting times - Poor reputational consequences from elongated waiting times - Regulatory challenges | 4 x 5 = 20 | C1) Formal recovery plan to be approved by Board of Directors in April with clear trajectories for recovery. Control Owner: Jonathan Mathews | Formal monthly reporting to the Board of Directors and IPC on progress against restoration and recovery. | North West performance report overseen by the C&M Hospital Cell. | Acceptable | 4 x 3 = 12 | NO | The Trust is not recurrently resourced to deliver levels of activity to recover the backlog of waiting lists and therefore there is a gap in assurance in delivering the recovery plan. | Annual Planning and Investment process in place to review investments for 22/23 Action Owner: Jonathan Mathews Due date: Further update April 2023 | Investments agreed through the Operational Board (May 22) to address the performance and quality gap for 22/23 targets. Strong performance against regional and national targets. Ongoing challenges for surgical log waiters and cancer diagnostics with action plans in place to progress. 23/24 annual planning on track for submission to ICS. Impact of industrial action is being reviewed and will be considered in annual planning. | 3 x 3 = 9 | 2023-03-31
|  |  | C2) Formal governance structure with clear roles and responsibilities in the Divisions through to Operational Board. Control Owner: Jonathan Mathews | Operational Board, 6 monthly reviews with all Divisions. |  | Acceptable |  |  | Recovery plans are based on full utilisation of current workforce and thus workforce resilience, recruitment and retention are potentially gaps in delivery. | Trust and Divisional plans in place in relation to workforce recruitment and retention. Action Owner: Jonathan Mathews Due date: Further update April 2023 | Workforce strategies in place, areas of concern and mitigating actions highlighted on the risk register and regularly reviewed with Divisions. Significant work undertaken to align admin structures to divisions and improve performance, with some delays in digital systems and future workforce plan to be determined in Q1 23/24. Impact of industrial action on staff morale and sustainability is being kept under review.
|  |  | C3) Weekly LHCH performance meeting reviewing KPIs in relation to demand, activity, waiting list growth. Control Owner: Jonathan Mathews | LHCH dashboard presented weekly to Executive Committee. | Contract review meetings | Acceptable |  |  | External factors - unmet demand as an output of the Covid pandemic. Unknown requirements of systemwide mutual aid. | Monitoring of key performance KPIs and demand data Action Owner: Jonathan Mathews Due date: Further update April 2023 | Dashboard and Trust SOF in place, reviewed weekly and monthly through the governance framework. Redesign of SOF agreed and progressing. Update presented to the Board Strategy Day in February 2023 with new SOF planned for 2023/24.
BAF3 Inability to achieve the five year capital programme within a challenging and uncertain operating environment and deliver an Estates Strategy that supports the provision of outstanding services Executive Risk Lead: Karen Edge, Chief Finance Officer Board Committee: Integrated Performance Committee Last Update: 14th March 2023 | Causes - Unknown implications of moving to an ICS capital envelope introducing competition and reducing freedoms - Large challenging capital programme and not knowing what may arise within a five year period - Two major capital schemes underway (+£20m) over a three year period and unknown developments during the complex programmes Consequences - Impact on delivery of LHCH capital plan - Inability to invest in innovations not currently identified in the Trust’s five year financial plan - Having to re-prioritise the programme if an unidentified need arises - Disruption to operational services during a complex capital programme | 4 x 3 = 12 | C1) Robust governance in place to provide assurance on the capital programme, documented through Capital Management Group to Operational Board. Control Owner: Karen Edge | Operational Board reporting to Board of Directors monthly. |  | Acceptable | 4 x 3 = 12 | NO | Uncertainty of the ICS capital envelope for the system | Clarity required on the impact of systemwide capital envelopes future years Action Owner: Karen Edge Due date: April 2023 | Trust capital allocation for 2022/23. The capital programme has been assessed and prioritised against the allocation. Opportunities to use charitable funds are also being explored. Ongoing engagement with the ICS on the allocations and risk based prioritisation. 2023/24 capital envelope confirmed. | 3 x 3 = 9 | 2023-03-01
|  |  | C2) Partnership / resilience with Propcare to deliver major schemes managed through Capital Programme Board. Control Owner: Karen Edge | Formal monthly report to the Operational Board and bi-monthly to the Board of Directors. |  | Acceptable
|  |  | C3) Formal process in place for capital planning and prioritisation including the impact of system wide capital envelopes. Control Owner: Karen Edge | Quarterly update to the Integrated Performance Committee, monthly capital updates to the Board of Directors. Estates Strategy approved. |  | Acceptable
|  |  | C4) Inspection and maintenance programme appropriate for age and condition of infrastructure. Control Owner: Karen Edge | Health and Safety Committee reports to Risk Management Committee and in turm to Operational Board. Quarterly capital updates to IPC and monthly capital updates to the Board of Directors. Prioritsation execise based on gap in capital funding allocation | Six Facet Survey | Partial |  |  | Clarity of risk profile of current infrastructure. | Critical infrastructure review to be undertaken to inform risk and prioritisation for future capital programme. Action Owner: Karen Edge Due date: Further update April 2023 | The capital programme has been assessed and prioritised against the allocation. Opportunities to use charitable funds explored. Inspection and maintenance programmes reviewed. The critical infrastructure review is progressing.
Return to Main Menu
Return to Main Menu

## Workforce
Risk Theme: Workforce
RISK APPETITE: SEEK - Upper tolerance limit 16
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO2: Advancing Quality & Innovation, SO4: Developing People
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF4 A deterioration in the physical and mental wellbeing of our workforce would hinder our ability to provide the best possible care, experience and outcomes for patients Executive Risk Lead: Karen Nightingall, Chief People Officer Board Committee: People Committee Last Update: 14th March 2023 | Causes - Increase in mental health issues - Staff with ‘long Covid’ - Further surges / new variants - Staff burn-out Consequences - Loss of goodwill and staff engagement - Fluctuating capacity - Increase in long-term sickness - Increased staff turnover | 4 x 5 = 20 | C1) The People Plan identifies the priority areas of focus for Wellbeing. Control Owner: Karen Nightingall | Quarterly report to People Committee on People Action plan progress and appointment of a Wellbeing Guardian for the Trust. Health and wellbeing Group. | NHS benchmarking on absence and turnover data. | Partial | 3 x 4 = 12 | YES | Assessment against the NHS Wellbeing Framework and development of a wellbeing strategy. | Complete the assessment against the NHS Wellbeing Framework and develop a Trust Wellbeing Strategy. Action Owner: Rachael MaDonald Due date: Further update April 23 | NHS Wellbeing Framework self assessment is complete. Development of the wellbeing strategy in progress. | 3 x 4 = 12 | 2023-03-01
|  |  | C2)The People Delivery group tracks sickness/absence and turnover and weekly reports and analysis are provided to Bronze command. Control Owner: Karen Nightingall | Quarterly reports on workforce performance are provided to People Committee. | National staff survey measures engagement. | Partial |  |  | Retention Strategy action plan to be delivered and assurance on outcomes needed. | Retention group actions to be delivered. Action Owner: Karen Nightingall/ Sue Pemberton Due date: Further update April 23 | Retention Group in place (covering the whole Trust) to take forward the retention strategy action plan. Retention summit held October 2022 and action plan developed to progress. Further retention summits held. Recruitment and retention processes have been digitised. Retention figures remain a challenge and action plan progress continues.
|  |  | C3) EAP programme, contract with Merseycare and alignment with principles of Improving People Practices (IPP) are reviewed by the People Delivery Group. Control Owner: Karen Nightingall | Quarterly reports on workforce health & wellbeing (as part of performance) are provided to People Committee. |  | Partial |  |  | Understanding resillience of the workforce. | Collaboration on occupational health is being progressed with Alder Hey and the contract with Merseycare on psychological support has been extended. Action Owner: Beth Williams-Lally Due date: Further update April 23 | Mental health collaboration with Merseycare. Mental Health advocates in place. Developed psychological support offer on a page. Mental health first aiders have all been trained and psychology champions established. Resources and funding needs to be addressed through annual planning to enable this risk to be mitigated in 2023/24.
|  |  | C4) Staff survey action plans Control Owner: Karen Nightingall | Updates through People Committee Divisional Governance Meetings to Operational Board |  | Acceptable |  |  | Staff survey results action plans and assurance. | Survey results and engagement index published and divisions working on key themes for improvement with HR support. Action Owner: Sarah Smith Due date: Further update April 23 | An overarching Trust action plan has been established as well as Divisional action plans. Communications are for 'you said, we did' in advance of 2022 survey. 2022 staff survey completion was good. New action plan will be developed when results are received in March 2023.
BAF5 If delivery of people development programmes continues to be constrained, workforce morale and quality of care may suffer Executive Risk Lead: Karen Nightingall, Chief People Officer Board Committee: People Committee Last Update: 14th March 2023 | Causes - Learning & development reprioritised due to Covid - Formal leadership development hindered (incl talent management / succession planning) Consequences - Erosion of skills and knowledge - Delays in onboarding - Reduced leadership capacity and capability - Reduced staff engagement - Increased staff turnover | 3 x 4 = 12 | C1) The People Plan identifies priority areas for OD & Education. Control Owner: Karen Nightingall | Quarterly report to People Committee on People Action plan progress. | CQC inspection and MIAA audits. Staff survey results. | Partial | 3 x 4 = 12 | YES | Delivery of L&D Strategy including Scope for Growth. | Deliver the L&D strategy action plan including Scope of Growth. Action Owner: Christina Chackalova Due date: Further update April 23 | L&D Strategy developed and progress against action plan. Scope for growth launched and will be rolled out in Q1 2023/24. | 3 x 4 = 12 | 2023-03-01
|  |  | C2) Mandatory training programmes 2021 ensures all staff skills are up to date. Control Owner: Karen Nightingall | Monthly mandatory training report to the People Delivery Group. |  | Partial |  |  |  | Further improvements to be made to e-learning. Action Owner: Sarah Smith Due date: Further update April 23 | E'learning developments continuing to progress. Current focus is on digitising the reporting to help the management and reporting of mandatory training compliance.
[9 empty] | Clarity of National expectations. | Continue to track and understand implications of national reviews for local action, and Ockenden actions. Action Owner: Karen Nightingall Due date: Further update April 23 | Continuing to deliver action plans in respect of learning from Ockenden.
BAF6 Challenges in retaining and recruiting a high quality, diverse and inclusive workforce would affect our ability to deliver world class care Executive Risk Lead: Karen Nightingall, Chief People Officer Board Committee: People Committee Last Update: 14th March 2023 | Causes - Perceptions of the NHS as a place to work post Covid - Competition for talent - Expectations of Millennials entering the labour pool - Exodus from NHS of patient facing staff - Poor staff morale - Staff burn-out Consequences - Nursing vacancy gap exacerbated - Increased bank/temp staff hours - Erosion of world-class specialist talent - Lack of leadership stability | 4 x 5 = 20 | C1) The People Plan identifies: recruitment and promotion of a diverse workforce, attracting and retaining the best national and international talent Control Owner: Karen Nightingall | Reports to Equality and Inclusion steering group and quarterly reporting to People Committee Retention Group updates. Recruitment and Retention Strategy EDIB Strategy Workforce dashboard and KPIs | National reporting on diversity data and information from Model Hospital for benchmarking Staff survey results | Partial | 3 x 4 = 12 | YES | Implementation of the recruitment strategy. | Implementation of the recruitment strategy Action Owner: Sarah Smith Due date: Further update April 23 | Recruitment and Retention Strategy in place. Retention summits continue to be held. Recruitment proceeses are being digitised inconjunction with Alder Hey. Recruitment days being held for scarce disciplines. Improved retention performance continues to be tracked. | 3 x 4 = 12 | 2023-03-01
|  |  | C2) Staff shortages - workforce reviews and recruitment campaign Control Owner: Karen Nightingall | Reports to People Delivery group and to the Recruitment and Heads of Nursing working group. Monthly Board reports on Nurse Staffing. |  | Partial |  |  | Vacancy gaps in range of professional groups including ODPs, radiographers and physiology staff. | Clear action plans to be developed in each area including recruitment campaigns, recruitment days and workforce reviews. Action Owner: Sarah Smith Due date: Further update April 23 | International nurse recruitment complete. Recruitment days undertaken for administration and healthcare assistants. Risks reflected on risk registers and subject to regular Divisional governance review. Recrutiment days being held and working with Univiersities to grow the pipeline.
[9 empty] | Action required to understand reasons and mitigate retention risks. | Retention group actions to be delivered. Action Owner: Karen Nightingall/ Sue Pemberton Due date: Further update April 23 | Retention group established and retention summits held. Ongoing work around retention. Retention group are making good progress. Retention figures remain a challenge.
Return to Main Menu
Return to Main Menu

## Finance
Risk Theme: Finance
RISK APPETITE: OPEN - Upper tolerance limit 12
LINKS TO STRATEGIC OBJECTIVES: | SO3: Increasing value
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF7 Failure to deliver financial plans and changes in the funding regime could impact sustainability for the Trust and system partners Executive Risk Lead: Karen Edge, Chief Finance Officer Board Committee: Integrated Performance Committee Last Update: 14th March 2023 | Causes - Changes to the commissioning regime - Increased costs associated with pandemic and recovery - Slow-down in commercial income - Ability to drive out further efficiencies while managing recovery Consequences - Ability to fund strategic plans | 4 x 3 = 12 | C1) Annual Budget Control Owner: Karen Edge | Financial Plan Board Report Mar/Apr 2022 | Financial Plan NHSI Template | Acceptable | 4 x 3 = 12 | YES | System approach to management of financial risk and allocation of resources | Focus on underlying position, and engagement with system finance leadership. Action Owner: Karen Edge Due date:Further update April 23 | Final budget approved by the Board with surplus aligned to system plan. Continue to monitor for in year risks and mitigations. Financial strategy reviewed at Board Strategy Day in February 2023 for approval April 2023. Continued collaboratively working with ICS and partners around C&M position for 2023/24. | 4 x 3 = 12 | 2022-05-01
|  |  | C2) CIP Plan Control Owner: Karen Edge | CIP Tracker IPC & FPG Apr22 & Mthly | Financial Plan NHSI Template | Acceptable |  |  | Under-developed CIP Plan | Development & Tracking of Schemes against Target Action Owner: James Bradley/DDoO's Due date: Further update April 23 | CIPs continue to be tracked with regular reports on progress to IPC and the Board. Identification of schemes is over 90% with mitigations for in-year slippage. Starting to look at 23/23 planning with early focus on CIP identification. CIP workshop held in January 2023 to support development of the 2023/24 CIP programme.
|  |  | C3) System of Budgetary control and oversight Control Owner: Karen Edge | Finance Report Board of Directors/IPC Bi-mthly/Qtrly IPC and FPG | NHSI Financial Performance Report template (Monthly) Internal Audit Plan (Annual) | Acceptable |  |  | Recovery of non-NHS income to pre covid levels including private patients and research. | Clear plans to be developed to recover non- NHS income to pre-covid levels. Action owner: Karen Edge/ Jonathan Mathews Date: Further update April 23 | Operational group established to focus on private patient recovery. (refer BAF 8 regarding research). Private patient income continues to fluctuate albeit improvements have been made in year but there are gaps in deliverying to pre-covid levels. Surgery Division delivering actions as part of their recovery plan.
Return to Main Menu
Return to Main Menu

## Innovation
Risk Theme: Innovation
RISK APPETITE: SEEK - Upper tolerance limit 16
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO2: Advancing Quality & Innovation, SO3: Increasing Value
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF8 Inability to drive the Research and Innovation agenda to exploit future opportunities Executive Lead - Dr Jay Wright (Research) and Jonathan Develing (innovation) Board Committee: Board of Directors Last Update: 14th March 2023 | Causes - Turnover of specialists - Reduced funding for R&D - Capacity of leadership for Innovation Function Consequences - Ability to maintain R&D function - Aligment of Innovation function with Strategic Partnerships | 3 x 4 = 12 | C1) Research Committee Control Owner: Jay Wright | Board report Exec sign off Grant applications Recruitment targets Research Committee reports through Ops Board | MIAA report to Audit Committee MHRA inspection | Partial | 3 x 4 = 12 | YES | Research Strategy | Update strategy and take to Execs, Ops Board and Board of Directors for ratification. Action Owner: Jay Wright Due date: Further update April 23 | Research strategy presented to Ops Board, BoD, CoG and research committee. Feedback reflected in to document which has been drafted. Monthly research report to Ops Board and quarterly to BoD. LCCS review To be undertaken 8th and 13th March with external facilitation from Prof Ajay Shah at Kings College. The Strategic R&I Committee is being established to provide oversight of research strategy development and delivery and first meeting took place 14th March 2023. | 3 x 4 = 12 | 2023-03-31
|  |  | C2) Ops Board Control Owner: Jay Wright | Internal staffing and recovery plan | MHRA inspection MIAA audit action plan complete. | Acceptable
|  |  | C3) Reports to CRN Control Owner: Jay Wright | Monthly meeting with CRN. Trials Management System. |  | Partial |  |  | Uncertainty regaridng funding and income streams. | Understand and influence CRN funding. Contingency actions to secure grants and commercial funding. Action Owner : Jay Wright Due date: Further update April 23 | Meeting with LCRN COO – funding in North West Coast allocated on historic basis only – LHCH payments will not change this year despite overperformance in 21-22 (> 1600 CVD patients). Allocation when NWC and GM merge may reflect performance in the future. Meeting with LCRN RDM – high level of sickness in LHCH and task force research nurses + many patients in FU from last years recruitment has reduced numbers this year. Strong pipeline and further comparative effectiveness study in patient safety being planned. On target for recruitment to portfolio studies.
|  |  | C4) CRF Arrangements | Updates through Operational Board. |  | Acceptable |  |  | New arrangements need to be established follwing successful bid for CRF with partner organisations. | Work with Partners to establish working agreements, resources, funding flows, delivery, reporting and assurance mechanisms for CRF. Action Owner: Jay Wright Due Date: Further update April 23 | Data manager in place, Band 7 nurse now in post. Funding for PPI and methodology clinic in place. Finance and Governance meetings arranged. Directors Board established. 2 early phase heart failure studies currently in review process. £300K capital bid submitted to update laboratory and pharmacy facilities.
|  |  | C5) Development of a new Strategy for Innovation Control Owner : Jonathan Develing | Executive Directors Operational Board Board of Directors |  | Partial |  |  | Innovation Strategy | Development of a new Strategy for Innovation Action Owner: Jonathan Develing Due Date: Further update April 23 | Innovation strategy development discussed at October 22 Board Strategy Day. Innovation strategy will be considered within the new Strategic R&I Committee (first meeting took place 14th March 2023).
BAF9 Failure to be recognized as an Anchor Institution, demonstrating social value, sustainable green strategy and contribution to population health may increase costs in the longer term and disappoint public, staff and regulatory expectations Executive Risk Lead: Jonathan Develing, Director of Strategic Partnerships Board Committee: Board of Directors Last Update: 14th March 2023 | Causes - Considered part of the Broadgreen site not just that of LHCH - Energy consumption not know at a local level (area by area) - Up-front investment required - Benefits poorly understood - No Cheshire & Merseyside Green Plan – many benefits should be delivered at scale (procurements / green EV fleets) - With competing priorities and other risks, the NHS commitment to net zero may not be seen as a high priority for investment Consequences - Reputation as a responsible healthcare provider - Failure to reduce waste and realise efficiencies - Disappointment of staff engaged with Green issues - Failure to contribute toward improving air quality - declared by the LA as a climate emergency | 2 x 4 = 8 | C1) Trust's Green Plan Control Owner: Jonathan Develing | Publication of the Trust Green Plan Interdependencies between Green Plan and Capital Program understood Year end review to BOD Mid Year report of benefit realisation to BoD | Completion of NHSE/I Template OKTA (quarterly submission) Trust submitted Green Plan to ICS by 14th January 22. ICS using Trust Green Plan as an exemplar Queens green canopy recognition | Partial | 2 x 2 = 4 | YES | Full realisation of benefits and initiatives in place Lost opportunities to access external grants that are not fully known Working at scale across Provider systems Unable to quanitfy the baseline metrics from which to measure a net zero position by 2040 | Exploring with the ICS options for external support in developing metrices for baseline assessments. Action Owner: Director of Strategic Partnerships Due Date: Further update April 23 | Trust has committed to COP26 pledge. Trust submitted Green Plan to ICS. Green champion working group established. Contribution to Broadgreen event on health and wellbeing (including green) April 22. Trust has achieved Social Value Award. Working with the Carbon Neutral Group, the Trust is now piloting a benchmarking analysis sponsored by the ICS to understand our baseline carbon consumptions and share learning with other organisations. Carbon Netral report presented to Board (Nov 2022). Workign with LUFT on site approach to green given interdependencies. Progress against green plan to be presented to the Board in February 2023. | 2 x 2 = 4 | 2023-03-01
|  |  | C2) Social Value Accreditation | Exec Group and Ops Board oversight. CEO Report to Board of Directors. | Social Value accrediation through ICS (Level 1) | Partial |  |  | Progress to level 2 | To begin working on the competencies for level 2 accreditation. Action Owner: Director of Strategic Partnerships Due Date: April 23 | Accredited at level 1 (Jan 2022).
|  |  | C3) Prevention Pledge | Exec Group and Ops Board oversight. CEO Report to Board of Directors. | ICS Health Equalities Group Quarterly return to ICB | Partial |  |  | Reporting and assurance arrangements | To establish assurance reporting of health inequalities and prevention work within the Trust. Action Owner: Director of Strategic Partnerships Due Date: April 23 | Prevention group in place. The Trust has been recognised as formally adopting the NHS Prevention Plan. An action plan, that supports the 14 core commitments of prevention has been established. Aurterly plan submitted to ICB along with tracker. Early work on health inequalities shared through the Board strategy days.
Return to Main Menu
Return to Main Menu

## System Working
Risk Theme: System Working and Collaboration
RISK APPETITE: SEEK - Upper tolerance limit 16
LINKS TO STRATEGIC OBJECTIVES: | SO2: Advancing Quality & Innovation, SO5: Leading through Collaboration, SO6: Population Health
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF10 The priorities of the ICS are developing and may present tensions for our strategic plans and collaborations and divert leadership capacity Executive Risk Lead: Jonathan Develing, Director of Strategic Partnerships Board Committee: Board of Directors Last Update: 14th March 2023 | Causes - Primary Legislative Changes as described in the White Paper - Maturity if the Health and Care Partnership as it forms the ICS - Development of Provider Collaborative - Changes in commissioning process - Unclear clinical priorities - Lack of defined strategy/plans Consequences - Conflicting priorities between LHCH and ICS - Diversion of LHCH leadership capacity - Loss of autonomy | 4 x 4 = 16 | C1) Legislative Changes - Standing item on Board Agenda Control Owner: Director of Strategic Partnerships | Chief Executive Briefing to BOD Quarterly Update on Board Agenda |  | Partial | 3 x 3 = 9 | YES | Uncertainty regarding levels of delegation and decision making. | Ensure the Trust has appropriate representation at the ICS, CMAST, Provider collaboratives, specialised commissioning and local place based (e.g. One Liverpool) governance forums Action Owner: Jonathan Develing Due date: Ongoing | Stakeholder mapping exercise complete. LHCH is participating in the Liverpool Clinical Services review. The Board has also approved the CMAST Joint Working Agreement and Committee in Common TOR. Liverpool clinical services review complete and Board commitment confirmed to ICB (the impact from the review will need to feature as part of 23/24 BAF). Broadgreen site committee has met in shadow format (March 2023). | 3 x 3 = 9 | 2022-01-01
|  |  | C2) Cardiovascular Board - Standing item on Board Agenda Control Owner: Director of Strategic Partnerships | CVD Board Papers CVD Board Newsletter Ops Board Briefing | Quarterly Cardiac Board highlight reports to ICB. | Partial |  |  |  | Development of the C&M CVD recovery plan through the CVD Board in partnership with the ICS. Action Owner: Jonathan Develing Due date: Further update April 23 | Good progress being made against the 4 national pathways. Highlight reports are provided to the ICB on a quarterly basis as an assurance mechanism for the Cardiac Board. ACS pathway is progressing through the cardiology collaborative. Advancing CVD Prevention now published (March 2023).
|  |  | C3) Single cardiology service developments - Standing item on Board Agenda Control Owner: Director of Strategic Partnerships | Executive and Operational Board iversight. Reports to the Board of Directors. | Independent Chair appointed to Cardiology Partnership Board. | Partial |  |  | Case for change, plan, resources, approach and timelines being explored. | Case for change, plan, resources, approach and timelines being explored and developed. Action Owner: Jonathan Mathews Due date: Further update April 23 | TOR, governance and reporting including MOUs approved. Workshops have been held for the 4 key workstreams and action plans progressing. Progress updates include a focus on the ACS working group with a pilot planned for Q4. The Cardiology Partnership Board meets 6 weekly, with regular Chairs briefings and updates to Board of Directors.
Return to Main Menu
Return to Main Menu

## Digital
Risk Theme: Digital
RISK APPETITE: OPEN - Upper tolerance limit 12
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO6: Population Health
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF11 Failure to ensure strong digital transformation and IT service resilience could erode LHCH’s position as a world-class provider of specialist care delivering services for patient needs Executive Risk Lead: Kate Warriner, Chief Digital & Information Officer Board Committee: Board of Directors Last Update: 14th March 2023 | Causes - Lack of capacity and capability for transformational change and operational delivery - Insufficient investment in IT infrastructure - Varied appetite for transformational change within teams - Increasing sophistication and variety of malicious attacks - Integration of networks across the ICS - Increased reliance on digitised processes - Legacy infrastructure requiring modernisation - Legacy processes, delivery and capability requiring modernisation Consequences - Clinical innovation hindered or poorly implemented - Negative reputational impact - Loss of leading position as provider of specialist services - Disruption to services - Loss of data - ICO fines - Fraud/theft | 4 x 3 = 12 | C1) Statement of Planned Benefits Control Owner: Associate Director Digital Transformation | Diigtal Strategy and Statement of Planned Benefits regulary reviewed at Digital Excellence Committee | NHS Digital Digital Aspirant Letter of Acceptance. NHS Digital approval of Digital Aspirant progress and associated funding. | Acceptable | 4 x 3 = 12 | YES | Statement of Planned Benefits Finalised, Approved and Monitored; NHS Digital Assessment | First draft of Statement of Planned Benefits to be presented at Digital Excellence Committee in May. NHS Digital Assurance process. Action Owner: Associate Director Digital Transformation Due date: Further update April 2023 | Statement of planned benefits tracked at Digital Excellence Committee. A number of benefits are being realised which are reported to the DEC through the programme highlight report. Expected funding approved for 2022/23. Full deep dive to be reported in Q4. | 3 x 4 = 12 | Q4 2021/22
|  |  | C2) Collaboration Partnership Agreement Control Owner: Chief Digital and Information Officer | Performance delivery reports; Approved Partnership Agreement | ISD Level 3 accreditation. | Acceptable
|  |  | C3) Cyber security Control Owner: Chief Digital and Information Officer | Cyber Management Reports to Audit Committee DSPT Submission The Trust has implemented systems to respond to and action NHS Digitals cyber alerts (Care Certs) DEC reporting. | Internal Audit reports Cyber Essentials Accreditation | Acceptable |  |  | Cyber essentials Plus | Achievement of cyber essential plus external accreditation Action Owner: Assistant CDIO - Delivery and Assurance Due date: Further update April 23 | Cyber controls remain in place. Progress continues with regards to cyber priorities and defences. Cyber capacity and capability further developing include cyber apprentice now in post.
[9 empty] | Issues securing experienced resources in some services High turnover in some elements of the digital service poses a risk to delivery in some programmes and activities. | Recruitment linked to new iDigital operating model underway; maximising opportunities of collaboration; and new service model in the process of being implemented. Action Owner: Chief Digital and Information Officer Due date: Further update April 23 | New operating model is embedded into practice. Work is underway to support talent management and succession planning. Substantive senior management recruitment completed and further recruitment to key roles has progressed well. Workforce development includes graduate, apprenticeships and internships.
|  |  | C4) Data analytics and BI Control Owner: Chief Digital and Information Officer | DEC reporting. |  | Acceptable |  |  | Delivery of the data analytics and BI development priorities. | Delivery of Data analytics and BI priorities Action Owner: Chief Digital and Information Officer Due date: Further update April 23 | Data analytics and BI plan approved by DEC with regular highlight reporting. Good progress being made against the 12 month plan and priorities including Power BI developments, new SOF and support to Divisional priorities.
Return to Main Menu
Return to Main Menu

## Reference page
Board Assurance Framework 2022/23
i) The BAF is presented thematically to show the different types of strategic risk that have been identified by the Board in relation to the delivery of the Trust's Strategic Plan
ii) A quarterly report on progress of the strategic objectives is provided separately to the Board
iii) The Board's risk appetite in relation to each risk theme is noted - this is based upon the Board's defined apppetite for risk as set out in the Risk Management Policy
iv) Each risk is assigned an inherent risk score to estimate the uncontrolled risk - when compared with the residual (current) score it allows the Board to understand how effective the risk response is
v) Each risk is also allocated a target risk score which indicates the expected level of risk by the end of the 2021/22 - this must be below the upper tolerance limit set for the risk theme and be forecast based on
planned actions
5x5 risk scoring matrix:
• Refer to BAF Policy for operating guidance, roles and responsibilities and reporting template
Risk Appetite Levels