## Slide 1: 2021/22 Operational Recovery
April 2022
Item 4.2
Jonathan Mathews. Chief Operating Officer

## Slide 2: Activity for 21/22
Elective recovery is focussing on delivering 19/20 (pre covid) levels of activity .
*figures subject to slight variance with flex/freeze position
Key pressure points:
*Bed capacity, urgent non elective demand and staffing additional capacity
Elective Recovery | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total
19/20 | 655 | 678 | 662 | 756 | 641 | 711 | 779 | 742 | 634 | 746 | 736 | 637 | 8377
21/22 Actual | 638 | 646 | 668 | 667 | 635 | 631 | 674 | 722 | 589 | 627 | 708 | 671 | 7876
Variance | -17 | -32 | +6 | -89 | +6 | -80 | -105 | -17 | -45 | -119 | -28 | +34 | -501
% Delivery | 97% | 95% | 101% | 88% | 99% | 89% | 87% | 97% | 93% | 84% | 96% | 105% | 94%

## Slide 3: 52 & 104 Week Planning
Key pressure points:
*Surgery Trajectory significantly impacted by urgent demand with Omicron impacting staffing for Q4
*LAAO, EP & Cardiac Surgery main sub specialty pressures (based on clinical prioritisation)
*All 52 week breaches have a completed harm review & are prioritised where possible
*All 104 week patients are re reviewed
104 Week | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Trajectory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 5 | 5
Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -4 | -5 | -5
52 Week | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Trajectory | 138 | 131 | 122 | 108 | 88 | 74 | 55 | 30 | 8 | 3 | 25 | 18
Actual | 121 | 103 | 107 | 96 | 85 | 72 | 54 | 45 | 62 | 52 | 49 | 54
Variance | -17 | -28 | -15 | -12 | -3 | -2 | -1 | +15 | +54 | +49 | +24 | +36

## Slide 4: 18 Week Trajectory
Divisional trajectories submitted for 21/22
Further review and modelling has been undertaken and the below Trust position has been created
18 Weeks | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Trajectory | 952 | 863 | 879 | 844 | 804 | 772 | 740 | 700 | 668 | 628 | 596 | 564
Actual | 869 | 839 | 829 | 877 | 799 | 777 | 791 | 675 | 697 | 687 | 700 | 774
Variance | -83 | -24 | -50 | +33 | -5 | +5 | +51 | -25 | +29 | +59 | +104 | +210
Key pressure points:
*Non admitted validation has been impacted by sickness and redeployment of resources to COVID support

## Slide 5: Clock Stops - Admitted
Admitted Actual | Oct | Nov | Dec | Jan | Feb | Mar
CARDIOTHORACIC SURG | 106 | 125 | 89 | 120 | 137 | 134
CARDIOLOGY | 298 | 331 | 272 | 285 | 272 | 283
CARDIOTHORACIC MEDICINE/SLEEP STUDIES | 28 | 22 | 21 | 38 | 23 | 17
TOTAL | 432 | 478 | 382 | 443 | 432 | 434
Admitted H2 | Oct | Nov | Dec | Jan | Feb | Mar
19/20 Actual | 357 | 345 | 273 | 349 | 336 | 264
21/22 % of 19/20 | 121% | 139% | 140% | 127% | 129% | 165%

## Slide 6: Clock Stops – Non-Admitted
Non-Admitted Actual | Oct | Nov | Dec | Jan | Feb | Mar
CARDIOTHORACIC SURG | 56 | 82 | 42 | 69 | 59 | 39
CARDIOLOGY | 430 | 372 | 336 | 344 | 269 | 324
CARDIOTHORACIC MEDICINE/SLEEP STUDIES | 302 | 332 | 194 | 231 | 195 | 269
TOTAL | 788 | 786 | 572 | 644 | 523 | 632
Non-Admitted H2 | Oct | Nov | Dec | Jan | Feb | Mar
19/20 Actual | 797 | 842 | 613 | 794 | 723 | 619
21/22 % of 19/20 | 99% | 93% | 93% | 81% | 72% | 98%

## Slide 7: P2 Position
P2 clinical target to have their procedure within 1 month

## Slide 8: Cancer Performance
Strong Performance for all indicators with Faster Diagnosis achieved for the first month in Dec:
Trajectory and action plan led by Surgery with cross divisional requirements for CT guided biopsy & EBUS
Staffing levels in CT have significantly impacting the position/recovery plans for Q4

## Slide 9: Risks, Constraints & Mitigations
Risks | LHCH constraints | Mitigations/Actions | RAG
Staffing | Short term sickness Long term gaps- national shortages (ODP/Radiographers) Staff morale/resilience | Command & control structure in place (Bronze, Silver & Gold) to review levels of sickness within the Trust Recruitment and retention strategy being developed led by Director of HR Divisional actions in place for key workforce areas (on the risk register) Health & wellbeing team in place to support staff | 
Non Elective Demand & Bed Capacity | ACS & urgent surgery demand P2 numbers Surgical pathway COVID + area segregation | Winter escalation protocol in place Tactical command meetings utilised at peak occupancy (in line with bed meetings) P2 position reviewed weekly and listings flexed accordingly Ward Red/Amber/Green pathways managed in line with infection prevention measures | 
Sub specialty case mix | ACHD & Aortic Surgery EP & LAAO | Divisional trajectories in place Reviewed in performance meetings Clinical validation/harm reviews completed in line with national guidance | 
Information capture/availability | PAS functionality EMIS system integration | SAFER pathway management group in place to review internal systems & processes BI partners involved in weekly performance Senior BI lead in place for weekly/monthly returns (signed of by Senior Ops team) | 
Cancer diagnostic capacity | CT guided biopsy EBUS PET scanning | Faster Diagnosis action plan in place led by Surgery Weekly Cancer PTL meeting and escalation to Performance CT & EBUS capacity has been reviewed in line with demand PET scanning managed through SLA with LUFT |