## Sheet1
PERFORMANCE IN INITIATING
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
133463 | 18/LO/1208 | 239580 | SOUNDSCAR | Yes | 2018-11-16 | 0 | 7 | 7 |  | 2018-11-09 | 2018-10-22 | 2018-11-09 | 2018-11-09 | Please Select... | 2018-11-09 | J - Other | No delay | Neither
133464 | 18/NW/0842 | 257007 | Clyz Labs | Yes | 2019-01-03 | -29 | 43 | 14 |  | 2018-12-20 | 2018-12-20 | 2018-11-20 | 2018-11-21 | Please Select... | 2019-01-03 | J - Other | No delays | Neither