## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
139638 | 18/HY/0500 | 250498 | EORP AF Registry | Yes | 2019-02-22 | 1 | 2 | 3 |  | 2019-02-19 | 2019-01-29 | 2019-02-20 | 2019-02-20 | Please Select... | 2019-02-20 | J - Other | No delays | Neither
139639 | 17/NW/0662 | 220156 | APPRAISE ATP | No |  | -239 |  |  |  | 2019-02-07 | 2018-03-22 | 2018-06-06 | 2018-06-13 | Please Select... | 2019-02-22 | E - Staff availability issues | Issues with regulatory documents and staffing issues to start this study up | Both