## Q2 20-21 PI
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to: | Options
161977 | 19/NW/0262 | 249747 | The SmartView CoVeRed | Yes | 2019-10-18 | 0 | 7 | 7 | 2019-06-21 | 2019-10-11 | 2019-06-21 | 2019-10-11 | 2019-10-11 |  | 2019-10-16 | Other | No delay | Neither
161978 | 19/YH/ 0301 | 268446 | A phase 2 study of ABBV-3067 alone and in combination with ABBV-2222 | Yes | 2019-12-11 | 9 | 28 | 37 | 2019-09-10 | 2019-11-04 | 2019-10-31 | 2019-11-11 | 2019-11-13 |  | 2019-12-03 | Other | No delay | Neither