## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to: | Errors | Warnings | Check Rows to Delete on Upload Submission
185828 | 16/WA/0156 | 204506 | UK Mini Mitral | Yes | 2020-12-15 | 50 | 25 | 75 | 2020-08-17 | 2020-10-01 | 2016-07-19 | 2021-11-18 | 2020-11-20 | Please Select... | 2020-11-24 | [9 empty] | Y | None | Neither
186023 | 19/LO/1064 | 260639 | Tight K Trials | Yes | 2021-08-02 | 71 | 17 | 88 | 2021-01-28 | 2021-05-06 | 2019-11-06 | 2021-05-06 | 2021-07-16 | Please Select... | 2021-07-27 |  | Y | [7 empty] | Y | Covid19 restrictions | Neither
186269 | 21/LO/0080 | 293186 | CF STORM Trial | Yes | 2021-08-13 | 42 | 30 | 72 | 2021-04-26 | 2021-06-02 | 2021-03-10 | 2021-07-14 | 2021-07-14 | Please Select... | 2021-08-13 | [9 empty] | Y | None | Neither
186270 | 20/NW/0275 | 283265 | TEMPEST | No |  | 139 |  |  | 2021-03-15 | 2021-03-16 | 2020-08-12 | 2021-05-11 | 2021-08-02 | Please Select... | 2021-08-02 | [9 empty] | Y | None | Neither