## Front Page
Return to Main Menu
Return to Main Menu
Board Assurance Framework
2023 - 24

## Quality & Patient Experience
Risk Theme: Quality & Patient Experience
RISK APPETITE: MINIMALIST - Upper tolerance limit 6
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO6: Population Health
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF1 Failure to maintain safety and quality and avoid harm would result in poorer patient & family experience Executive Risk Lead: Joan Mathews, Director of Nursing and Quality Board Committee: Quality Committee Last Update: March 2024 | Causes - Covid part of the long-term operating context - Population health needs change due to long-term effects of Covid - Further surges / new variants - Insufficient workforce capacity - Staff wellbeing - Nosocomial outbreaks - Patients may present more clinically unwell due to longer waiting times - A higher proportion of patients with psychological/mental health issues post covid Consequences - Poorer patient experience - Less favourable patient outcomes - Ability to maintain CQC ‘outstanding’ - Patients not treated promptly and within waiting time targets - Deterioration in positive feedback from patients and families and negative patient survey results - Failure to implement the principles from the national safety strategy | 5 x 4 = 20 | C1) The quality and safety strategy 2021-24 sets out the workstreams to ensure the hosiptal delivers high quality and safe care. Control Owner: Joan Mathews | IPC BAF Quarterly reports and incident reports to the Board of Directors. Quality strategy progress reports to Quality Committee and Board of Directors. Quality dashboard to Qualtiy Committee and KPIs to Board of Directors. Learning from external reviews. QI plan updates to Operational Board. PSIRF implementation plan and updates to Quality Committee. GIRFT updates to Operational Board. In-phase implementation updates to Operational Board via Risk Management Committee. | National inpatient survey results. Healthwatch reports. Internal audit reviews. NHS Staff survey results | Acceptable | 3 x 2 = 6 | YES | Implementation of new patient safety framework (PSIRF), new incident reporting system (In Phase) and LFPSE. | To implement the new patient safety framework across the Trust. Action Owner: Joan Mathews Due date: Quarterly updates | Quality strategy progress reports in place. Patient Safety Incident Response Framework (PSIRF) live, with the policy and plan now approved by LHCH and the ICB. Patient Safety Lead, patient safety partners and patient safety champions established with safety walkabouts taking place. In-phase implementation significantly progressed with a number of modules now live. In-phase reporting functionality continues to be developed. PSIRF learning and reporting aspects continue to be enhanced. New quality and safety strategy priorities to be developed for 2025-28. | 3 x 2 = 6 | 2023-03-01
|  |  | C2) Infection Prevention and Control. Control Owner: Manoj Kuduvalli | IPC reports (including BAF) to the Board of Directors. Water and ventilation safety, antimicrobial stewardship, sepsis, and SSI committees reporting to Infection Prevention Committee to QSEC and Qualtiy Committee. Quality dashboard. | CQC reports and rating | Acceptable |  |  | Further work being undertaken regarding Surgical Site Infections (SSIs). Improvements being made for sepsis screening. | Ongoing monitoring of SSIs. Continued improvement in sepsis screening. Action owner: Manoj Kuduvalli Due Date: Quarterly updates | Action plan in place and progressing, as reported throush quarterly DIPC report. Further analysis of SSIs reviewed at Quality Committee, to be revisited in 12 months to look at more clinical stratification data. Continued monitoring in place. Detailed risk adjusted data fed back to clinicians and digital dashboard being developed for ongoing use.
|  |  | C3) EECS and CQC mock inspections process. Control Owner: Joan Mathews | IICC report 6/12 and complaints reports anuually. EECS and internal CQC mock assessments reported to Board. | Commissioner reviews of quality (quarterly) | Acceptable |  |  | Alignment to new CQC assessment framework. | To align EECS and CQC mock assessments to new CQC assessment framework. Action Owner: Joan Mathews Due date: Quarterly updates | Update to EECS assessment process progressing to reflect new CQC assessment framework with a plan to cover all areas in 2024/25.
|  |  | C4)The organisational learning plan for the Trust supports improvements in practice and care for patients. Control Owner: Karan Wheatcroft | Organisation learning reported through various forums including Operational Board and via QSEC to Quality Committee. Board of Directors receives ICCI reports and learning from deaths updates (quarterly). Organisational learning strategy approved by Board through CGM. | GIRFT reports and associated action plans | Partial |  |  | Failure to embed the learning from incidents could impact on patient safety and quality. | Roll out of learning database. Action Owner: Karan Wheatcroft Due Date: July 2024 | Organisational learning continues to be well embedded and update paper reported to Audit Committee July 2023. Weekly patient safety meeting is providing a great forum for sharing early learning from PSIRF and communication from this is being developed to enaure cascade. In-Phase reporting has progressed and systme functionality continues to be enhanced. The organisational learning database has been rolled out for mortality, and the Trust's Patient Safety Lead is working with clinicians to raise awareness and use of the database. Wider use of the database to be revisited.
|  |  | C5) Quality Governance Structure - QSEC, and Quality Committee. Control Owner: Joan Mathews | QIA process for CIP reporting through Quality Committee. Quality dashboard reporting through Quality Committee and KPIs to Board. Annual review of Committee effectiveness. Clinical policies and guidelines approved through governance structure. Quality Committee BAF key issues report. National and local audits reported through CAEG. | CQC Insight report to Board of Directors twice yearly. | Acceptable |  |  | CQC are revising their strategy therefore there may be changes to their inspection criteria. | Keep abreast of changes to the CQC strategy and embed into the trusts EECS process as required. Progress Well led self assessment. Action owner: Joan Mathews Due Date: Quarterly updates | EECS assessments in place. Also actively learning from other CQC inspections. Regular contact maintained with the CQC through relationship meetings. Exec to Exec meeting took place in May 2023. Well led self assessment complete. Updates to EECS progressing to reflect new CQC assessment framework as reflected above. Work planned to map well led self assessment to new CQC assessment process and engage at all levels.
|  |  | C6) Review of deaths Control Owner: Manoj Kuduvalli | Mortality improvement group reporting through the Quality Committee. Medical examiners. Mortality review group. | Dr Foster benchmarking | Acceptable
|  |  | C7) Implementation of Clinical Strategy Control Owner: Manoj Kuduvalli | Draft LHCH Clinical Strategy in place. |  | Partial |  |  | System clinical strategy. | Year 1 and 2 objectives to be determined and delivered. The strategy will also need to be reviewed to ensure alignment to system strategy once developed. Action owner: Manoj Kuduvalli Due Date: Quarterly updates | LHCH clinical strategy being further reviewed and refined including cardiology partnership developments. Divisional horizon scanning presented to Operational Board and Clinical Leads in September 2023. Awaiting system clinical strategy. Clinical strategy priorities clearly articulated as part of the LHCH strategy refresh. Increased emphasis on system and collaborative working on future strategic direction.
Return to Main Menu
Return to Main Menu

## Operational Effectiveness
Risk Theme: Operational Effectiveness
RISK APPETITE: CAUTIOUS - Upper tolerance limit 9
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO6: Population Health
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF2 Inability to deliver annual planning activity and performance targets could result in poorer patient outcomes, inability to address the backlog of patients waiting and result in financial consequences to the Trust. Executive Risk Lead: Jonathan Mathews, Chief Operating Officer Board Committee: Integrated Performance Committee Last Update: March 2024 | Causes - Insufficient capacity to deliver expected levels of activity - Gaps in workforce - Impact of industrial action - Unmet demand that did not present / get referred to services during the height of the pandemic, leading to a significant increase in the waiting list, above core funded capacity - Further surges / new variants - Backlog patients’ conditions have worsened while waiting - Pressures of mutual aid requirement based on system priorities Consequences - Inability to meet statutory waiting list / access targets - Failing to acheive SOF level 1 - Poorer patient outcomes and experience with extending waiting times - Poor reputational consequences from elongated waiting times - Regulatory challenges | 4 x 5 = 20 | C1) Annual plan with clear activity trajectories. Control Owner: Jonathan Mathews | Formal monthly reporting to the Board of Directors and IPC on activity against plan. | North West performance report overseen by ICS. | Acceptable | 4 x 3 = 12 | NO | The Trust is not recurrently resourced to deliver levels of activity. Capacity and estates to deliver increased activity. | Annual Planning and Investment process in place to review investment priorities for 23/24 Action Owner: Jonathan Mathews Due date: Quarterly update | Strong performance against regional and national targets. Ongoing challenges for surgical long waiters and cancer diagnostics with action plans in place to progress. 23/24 performance and financial plan trajectories submitted. Annual planning investment decisions agreed through Operational Board May 2023. Annual planning for 2024/25 commenced in December 2023. Awaiting annual planning national guidance. | 3 x 3 = 9 | 2024-03-31
|  |  | C2) Formal governance structure with clear roles and responsibilities in the Divisions through to Operational Board. Control Owner: Jonathan Mathews | Operational Board reporting. IPC reporting. |  | Acceptable |  |  | Plans are based on full utilisation of current workforce and thus workforce resilience, recruitment and retention are potentially gaps in delivery. Future impact of industrial action unknown. | Trust and Divisional plans in place in relation to workforce recruitment and retention. Action Owner: Jonathan Mathews Due date: Quarterly update | Workforce strategies in place, areas of concern and mitigating actions highlighted on the risk register and regularly reviewed with Divisions. Impact of industrial action on staff morale and sustainability is being kept under review. Workforce analytics being brought together to support annual planning for 2024/25.
|  |  | C3) KPIs and performance trajectories Control Owner: Jonathan Mathews | LHCH dashboard reviewed weekly through Performance meeting and Executive Committee. Monthly SOF report to Board and Operational Board. IPC reports. Patient Pathway and Administration Group reporting to Operational Board. | Contract review meetings. | Acceptable |  |  | Unmet demand as an output of the Covid pandemic. Unknown requirements of systemwide mutual aid. Safe waiting list management assurances. | Safer waiting list management actions and assurances being further developed. Safe 20 report to be drafted for contract and MIAA internal audit planned Q4. Action Owner: Jonathan Mathews Due date: Quarterly updates | End to end risk review completed and actions progressing around process mapping, SOPs and training. Safe waiting list management TOR approved through Operational Board and consolidated action plan being progressed. Waiting lists continue to be clinically prioritised for long waiters and urgent patients. Interdependencies of digital projects being reviewed. Quarterly updates to Operational Board. Significant Risk identified as part of EPRO implementation, mitigating actions progressing and learning to be picked up through PSIRF process.
BAF3 Inability to achieve the five year capital programme within a challenging and uncertain operating environment and deliver an Estates Strategy that supports the provision of outstanding services Executive Risk Lead: James Thomson, Chief Finance Officer Board Committee: Integrated Performance Committee Last Update: March 2024 | Causes - Implications of ICS capital envelope with undetermined ICB estates strategy and capital prioritisation process - Ageing estate and challenging backlog maintenance risks - Cath lab major capital scheme in its final year with contingency financial risk Consequences - Impact on delivery of LHCH capital plan - Inability to invest in innovations not currently identified in the Trust’s five year financial plan - Having to re-prioritise the programme if an unidentified need arises - Disruption to operational services during a complex capital programme | 4 x 3 = 12 | C1) Robust governance in place to provide assurance on the capital programme, documented through Capital Management Group to Operational Board. Control Owner: James Thomson | Operational Board reporting to Board of Directors monthly. |  | Acceptable | 4 x 3 = 12 | NO | Uncertainty of the ICS capital envelope for the system, estates strategy and capital prioritisation process. | Clarity required on the impact of systemwide capital envelopes future years Action Owner: James Thomson Due date: Quarterly updates | The capital programme has been assessed and prioritised against the allocation. Opportunities to use charitable funds continue to be explored. Ongoing engagement with the ICS on the allocations and risk based prioritisation. ICB has confirmed capital envelope is fully committed for 2023/24 and early notification received of initial 2024/25 allocation. | 3 x 3 = 9 | 2024-03-01
|  |  | C2) Partnership / resilience with Propcare to deliver major schemes managed through Capital Programme Board. Control Owner: James Thomson | Formal monthly report to the Operational Board and bi-monthly to the Board of Directors. |  | Acceptable
|  |  | C3) Formal process in place for capital planning and prioritisation including the impact of system wide capital envelopes. Control Owner: James Thomson | Quarterly update to the Integrated Performance Committee, monthly capital updates to the Board of Directors. Estates Strategy approved. |  | Acceptable |  |  |  | Review of capital contingency at system level and opportunity to bid for additional funding. Action Owner: James Thomson Due date: Quarterly updates | Additional capital allocation of £4M achieved for 23/24 to support development of strategic priorities including Cath Lab 7.
|  |  | C4) Estates strategy in place, including inspection and maintenance programme appropriate for age and condition of infrastructure. Control Owner: Jonathan Mathews | 6 monthly estates strategy update to BoD. Health and Safety Committee reports to Risk Management Committee and in turm to Operational Board. Quarterly capital updates to IPC and monthly capital updates to the Board of Directors. Prioritsation execise based on gap in capital funding allocation | Six Facet Survey. Regulatory and statutory assurance received ad hoc (e.g. fire safety, H&S etc). | Acceptable
Return to Main Menu
Return to Main Menu

## Workforce
Risk Theme: Workforce
RISK APPETITE: SEEK - Upper tolerance limit 16
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO2: Advancing Quality & Innovation, SO4: Developing People
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF4 Challenges in recruiting, developing, retaining and ensuring the wellbeing of a high quality, diverse and inclusive workforce would affect our ability to deliver world class care Executive Risk Lead: Jane Royds, Interim Chief People Officer Board Committee: People Committee Last Update: March 2024 | Causes - Perceptions of the NHS as a place to work post Covid - Competition for talent - Expectations of Millennials entering the labour pool - Exodus from NHS of patient facing staff - Poor staff morale - Staff burn-out - Increase in mental health issues - Staff with ‘long Covid’ - Further surges / new variants - Staff burn-out - Industrial action Consequences - A deterioration in the physical and mental wellbeing of our workforce - Loss of goodwill and staff engagement - Fluctuating capacity - Increase in long-term sickness - Increased staff turnover - Staff vacancy gaps exacerbated - Increased bank/temp staff hours - Erosion of world-class specialist talent - Lack of leadership stability - Erosion of skills and knowledge - Delays in onboarding - Reduced leadership capacity and capability - Reduced staff engagement - Increased staff turnover | 4 x 5 = 20 | C1) People Strategy delivery Control Owner: Jane Royds | Quarterly reports to People Committee. Bi-annual reports to the Board. | Staff survey results. MIAA audits. | Acceptable | 4 x 3 = 12 | YES |  |  |  | 4 x 3 = 12 | 2024-04-01
|  |  | C2) Recruitment and Retention Strategy delivery Control Owner: Jane Royds | Reports to People Delivery group and to the Recruitment and Heads of Nursing working group. Monthly Board reports on Nurse Staffing. Retention group reports to People Committee. | Staff survey results. Turnover KPI. OH data and Model Hospital data. | Partial |  |  | Vacancy gaps in range of professional groups including ODPs, Radiographers and Therapies. There is also a workforce risk in admin recruitment and retention | Clear action plans to be developed in each area including recruitment campaigns, recruitment days and workforce reviews. Action Owner: Peter Cook Due date: Quarterly updates | Recruitment days undertaken for administration, scrub staff and therapies. A retention summit took place in January 2024 to consider further actions to improve retention in hotspot areas. A range of successful recruitment events have taken place, which has resulted in full establishment in Theatres. Plans are being developed to address the challenges in Admin across all divisions, including role design to make roles more attractive and support succession to planning. Annual workforce planning has commenced with pro-active planning/recruitment being considered (e.g similar model to Nursing).
|  |  | C3) Culture and Wellbeing strategy Control Owner: Jane Royds | Quarterly report to People Committee on People Action plan progress and appointment of a Wellbeing Guardian for the Trust. Health and wellbeing Group. Improving People Practice bi-annual report to People Committee and annual to Board. | Staff survey results. NHS benchmarking on absence and turnover data. | Acceptable |  |  |  | Delivery of the Culture and Wellbeing action plan. Action Owner: Steph Keelan Due date: Quarterly update | Strategy has been approved by Board and launched with action plan. 2023 staff survey results received with LHCH rated top in the country. LHCH continue to grow its Live Well, Work Work Health and Wellbeing events in collaboration with Strategic Partnerships and as part of the Broadgreen Collaborative.
[10 empty] | Collaboration on occupational health is being progressed with Alder Hey and the contract with Merseycare on psychological support has been extended. Action Owner: Steph Keelan Due date: Quarterly updates | Increased funding is in place until end of March with a business case being prepared to support the continuation of this. Reflective space for managers has been introduced and Training for ‘Hot Debriefs’ have been rolled out across relevant areas and additional support in high pressured clinical areas continues. Further training for 'Hot Debriefs and Manager Reflective Practice' delivered. Joint OH Tender Process with AH to commence
|  |  | C4) Equality, Diversity, Inclusion and Belong Strategy delivery Control Owner: Jane Royds | Reports to Equality and Inclusion steering group and quarterly reporting to People Committee Retention Group updates. Recruitment and Retention Strategy EDIB Strategy Workforce dashboard and KPIs | National reporting on diversity data and information from Model Hospital for benchmarking Staff survey results on WRES and DES. | Partial |  |  | Delivery EDIB Y2 action plan and NHS EDI improvement plan. Anti racist framework (although not mandated). | Deliver the EDIB Y2 action plan and Anti Racist Framework Bronze level. Action Owner: Rachael McDonald Due date: Quarterly updates | Staff networks developed and several launched. A range of awareness events have been held. Anti Racist Framework went to Board in September and a communication plan has been developed to relaunch LHCH Anti Racism Commitment Statement EDI action plans were presented to the People Committee in December. An EDI Dasboard has been developed to monitor progress against the NHS Improvement Plan (to be presented to People Commitee in March) EDI specific Board objectives agreed in lne with the NHS Improvement Plan.
|  |  | C5) Learning and Development Strategy delivery Control Owner: Jane Royds | Quarterly report to People Committee on People Action plan progress. | CQC inspection and MIAA audits. Staff survey results. | Partial |  |  | Delivery of L&D Strategy including Scope for Growth. | Deliver the L&D strategy action plan including Scope of Growth. Action Owner: Christina Chackalova Due date: Quarterly updates | Talent Management was built in the Appraisal process for 2023 - achieving above 90% compliance. Training Needs Analysis being developed (q4) to indentify area of focus. Plans being discussed to improve experience of AHP workforce.
|  |  | C6) Workforce Planning Control Owner: Jane Royds | Annual Plan approved. | Annual plan submitted to ICS. | Partial |  |  |  | To submit workforce plan Action Owner: Chief People Officer Due date: Quarterly updates | First draft plan submitted and monthly meetings taking place with ICB CPO. Currently the only Trust in C&M planning on the no growth assumption required by the ICB.
|  |  | C7) Leadership and Succession Planning Control Owner: Val Davies | Annual Executive and NED succession plans reported to respective Remuneration Committees. |  | Partial |  |  | Comprehensive Board succession plan. | To develop a comprehensive Board succession plan and actions. Action Owner: Chief Executive / Chair Due date: Quarterly updates | Remuneration Committee (Execs) discussed risks and succession plan in November 2023. CEO appointment confirmed, Director of Nursing interim position confirmed and other director posts will be managed accordingly. CFO appoointment approved at Remuneration Committee (Execs). Director of Strategy and Director of Corporate Governance and Risk appointments confirmed. NED recruitment approved COG. Board recrutiment has resulted in full establishment with all Directors to be in post by June 2024.
Return to Main Menu
Return to Main Menu
Return to Main Menu
Return to Main Menu

## Finance
Risk Theme: Finance
RISK APPETITE: OPEN - Upper tolerance limit 12
LINKS TO STRATEGIC OBJECTIVES: | SO3: Increasing value
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF5 Failure to deliver financial plans and changes in the funding regime could impact sustainability for the Trust and system partners Executive Risk Lead: James Thomson, Chief Finance Officer Board Committee: Integrated Performance Committee Last Update: March 2024 | Causes - system financial control total and duty to collaborate system financial sustainability - Changes to the commissioning regime - Increased costs associated with post pandemic recovery - Slow-down in commercial income - Ability to drive out further efficiencies while managing recovery Consequences - Ability to fund strategic plans | 4 x 3 = 12 | C1) Finance Strategy Control Owner: James Thomson | Financial Plan Board Report | System Financial Plan ICB submissions | Acceptable | 4 x 3 = 12 | YES | System approach to management of financial risk and allocation of resources | Focus on underlying position, and engagement with system finance leadership. Action Owner: James Thomson Due date: Quarterly updates | Final 2023/24 budget approved by the Board with surplus aligned to system plan. Continue to monitor for in year risks and mitigations. LHCH financial strategy approved May 2023. Continued collaborative working with ICS and partners around C&M position, and strong engagement from LHCH including agreement in Q3 to increase contribution by £2.5M non recurrently. C&M financial strategy development has commenced with engagement from CFO community and medium term financial modelling is complete. Expenditure assurance protocol introduced by the ICB and operating for some organisations. | 4 x 3 = 12 | 2022-05-01
|  |  | C2) Annual Budget and systems of budgetary control Control Owner: James Thomson | Financial Plan (approved) Finance Report to BoD Board of Directors/IPC Bi-mthly/Qtrly IPC and FPG | Financial Plan ICB submissions Internal Audit Plan (Annual) | Acceptable
|  |  | C3) CIP Plan Control Owner: James Thomson | CIP Tracker IPC & FPG April & Mthly | Financial Plan NHSI Template | Acceptable |  |  | Under-developed CIP Plan | Development & tracking of schemes against target Action Owner: James Bradley/DDoO's Due date: Quarterly updates | Development of 2023/24 CIP programme underway with trajectory in place for identification against targets. CIPs continue to be tracked with regular reports on progress to IPC and the Board. CIP workshop held in January 2023 to support development of the 2023/24 CIP programme. Check and challenge sessions with Divisions continued into Q4 to drive identification and delivery of CIP schemes.
Return to Main Menu
Return to Main Menu

## Innovation
Risk Theme: Innovation
RISK APPETITE: SEEK - Upper tolerance limit 16
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO2: Advancing Quality & Innovation, SO3: Increasing Value
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF6 Inability to delivery the Research and Innovation agenda to exploit future opportunities Executive Lead - Dr Jay Wright (Research) and Jonathan Develing (innovation) Board Committee: Board of Directors Last Update: March 2024 | Causes - Turnover of research nurses - Reduced funding for R&D - Capacity for data analytics - Capacity of leadership for Innovation strategy Consequences - Ability to maintain R&D function - Aligment of Innovation | 3 x 4 = 12 | C1) Research Strategy Control Owner: Jay Wright | Board reports Strategic R&I Committee Grant applications Recruitment targets Operational Research Committee reports through Operational Board | Collaboration with wider research Network via LHP, regional research directors forum, LCCS strategic committee and Liverpool CRF strategic committee. ICB research landscape yet to be clarified | Acceptable | 3 x 4 = 12 | YES |  |  |  | 3 x 4 = 12 | 2023-03-31
|  |  | C2) Team structure, SOPs and expertise | Grant applications Recruitment targets Operational Research Committee reports through Operational Board Governance team restructure | MHRA Audit reports, MIAA review, CRF operational and governance boards | Acceptable
|  |  | C3) CRN Arrangements Control Owner: Jay Wright | Monthly meeting with CRN. Trials Management System. | Merger of NWC and CM LCRNs will provide new structure and KPIs next year | Partial |  |  | Uncertainty regarding funding and income streams. | Understand and influence CRN funding. Contingency actions to secure grants and commercial funding. Action Owner : Jay Wright Due date: Quarterly updates | Meeting with LCRN COO – funding in North West Coast allocated on historic basis only – regardless of overperformance. Allocation when NWC and GM merge may reflect performance in the future. Meeting with LCRN RDM – high level of sickness in LHCH and task force research nurses + many patients in FU from last years recruitment has reduced numbers this year. Strong pipeline and further comparative effectiveness study in patient safety being planned. On target for recruitment to portfolio studies. Ongoing discussions with CRN. Prioritsation of grant applications via LCCS review and internal LHCH investigator leadership of grant applications.
|  |  | C4) CRF Arrangements | Updates through Operational Board. | CRF Board | Acceptable
|  |  | C5) Development of a new Strategy for Innovation Control Owner : Jonathan Develing | Executive Directors Operational Board Board of Directors |  | Partial |  |  | Innovation Strategy | Development of a new Strategy for Innovation Action Owner: Jonathan Develing Due Date: Quarterly updates | Senior expertise secured from Innovation Agency to drive forward the development of the Innovation Strategy. Operational Board and Clincal leaders engaged (June 2023), one to ones with Executive Directors, Divisions and a range of stakeholders complete. Draft innovation strategy presented to Operational Board and Clinical Leads in September 2023. Final draft strategy presented to Exectuive Directors in March 2024, informing portfolios for 24/25. Discussions ongoing on operationalising the strategy alongside programme management, transformation workstreams and improvement projects.
BAF7 Failure to be recognized as an Anchor Institution, demonstrating social value, sustainable green strategy and contribution to population health may increase costs in the longer term and disappoint public, staff and regulatory expectations Executive Risk Lead: Jonathan Develing, Director of Strategic Partnerships Board Committee: Board of Directors Last Update: March 2024 | Causes - Considered part of the Broadgreen site not just that of LHCH - Energy consumption not know at a local level (area by area) - Up-front investment required - Benefits poorly understood - With competing priorities and other risks, the NHS commitment to net zero may not be seen as a high priority for investment Consequences - Reputation as a responsible healthcare provider - Failure to reduce waste and realise efficiencies - Disappointment of staff engaged with Green issues - Failure to contribute toward improving air quality - declared by the LA as a climate emergency | 2 x 4 = 8 | C1) Trust's Green Plan Control Owner: Jonathan Develing | Publication of the Trust Green Plan Interdependencies between Green Plan and Capital Program understood Year end review to BOD Mid Year report of benefit realisation to BoD. Anchor institute reports to Board. | Completion of NHSE/I Template OKTA (quarterly submission) Trust submitted Green Plan to ICS by 14th January 22. ICS using Trust Green Plan as an exemplar Queens green canopy recognition Cheshire and Merseyside Green Plan alignment | Acceptable | 2 x 2 = 4 | YES |  |  |  | 2 x 2 = 4 | 2023-03-01
|  |  | C2) Social Value Accreditation | Exec Group and Ops Board oversight. CEO Report to Board of Directors. Anchor institute reports to Board. | Social Value accrediation through ICS (Level 1) | Acceptable |  |  | Progress to level 2 | To begin working on the competencies for level 2 accreditation. Action Owner: Director of Strategic Partnerships Due Date: Quarterly updates | Accredited at level 1 (Jan 2022). The Trust has been awarded the social value quality mark bronze accreditation in Februrary 2024.
|  |  | C3) Prevention Pledge | Exec Group and Ops Board oversight. CEO Report to Board of Directors. Annual prevention plan report to Board of Directors. Anchor institutes report to Board. | ICS Health Equalities Group Quarterly return to ICB | Acceptable
|  |  | C4) Population Health and Health Inequalities workstream | Reporting to Board of Directors | ICS Health Equalities Group | Partial |  |  | Progress against plans, and development of reporting and assurance arrangements | To establish assurance reporting of population health and health inequalities work within the Trust. Action Owner: Director of Strategic Partnerships Due Date: Quarterly updates | Early work on health inequalities shared through the Board strategy day. Update provided to Board in May 2023. The Trust is now working with Place through the long term conditions group for the Liverpool population. CIPHA enhanced surveillance tools, and CVD Prevent being used as a means of identifying those areas of inequality within Place relating to heart and lung disease. This information is being used strategically by the Long Term Conditions Group to direct partners in the deployment of resources. Dedicated data collection exercise on safe waiting list management identifying those with protected characteristics in order to ensure prioritisation as appropriate. Board maturity for health inequalities was assessed by the Board using the NHS Providers questionaires in March 2024 demonstrating high level of confidence in the progress being made.
Return to Main Menu
Return to Main Menu

## System Working
Risk Theme: System Working and Collaboration
RISK APPETITE: SEEK - Upper tolerance limit 16
LINKS TO STRATEGIC OBJECTIVES: | SO2: Advancing Quality & Innovation, SO5: Leading through Collaboration, SO6: Population Health
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF8 System architecture is still maturing and may present tensions for our LHCH leadership role, alignment of priorities with the ICS and system partners, and ensuring wider view to Cheshire & Merseyside and beyond. Executive Risk Lead: Jonathan Develing, Director of Strategic Partnerships Board Committee: Board of Directors Last Update: March 2024 | Causes - Primary Legislative Changes as per the Health and Care Act 2022 - Maturity of the ICS and Place - Further development of Provider Collaboratives - Changes in commissioning process - Unclear clinical priorities - Newly defined system strategy/ plans Consequences - Conflicting priorities between LHCH and ICS - Diversion of LHCH leadership capacity - Loss of autonomy - Disruption to established clinical networks | 4 x 4 = 16 | C1) Legislative Changes - Standing item on Board Agenda Control Owner: Director of Strategic Partnerships | Chief Executive Briefing to BOD Quarterly Update on Board Agenda Papers on Code of Governance compliance, provider licence and addendum for Governors | CMAST CiC reporting to BoD | Acceptable | 3 x 3 = 9 | YES | Uncertainty regarding levels of delegation and decision making. | Ensure the Trust has appropriate representation at the ICS, CMAST, Provider collaboratives, specialised commissioning and local place based (e.g. One Liverpool) governance forums Action Owner: Jonathan Develing Due date: Quarterly updates | Stakeholder mapping exercise complete. LHCH is participating in the Liverpool Clinical Services review. The Board has also approved the CMAST Joint Working Agreement and Committee in Common TOR. Liverpool clinical services review complete and Board commitment confirmed to ICB. Broadgreen site committee has met in shadow format (March 2023) and TOR now being revised following the establishment of the overarching Liverpool Trust Joint Committee (TOR to be reviewed and approved by the Board in July 2023). A number of workshops have been held between LUHFT and LHCH to explore collaboration opportunities and priorities. Briefing provided to Board on partnership arrangements in primary care (September 2023) and update on provider partnerships and collaborations planned for November 2023. Rolling programme of reports will include industry, voluntary sector and academia. System governance update reported to Audit Committee in October 2023. Exectutive portfolios have been realigned, and transiition arrangements including strategic partnerships have been established. | 3 x 3 = 9 | 2022-01-01
|  |  | C2) Cardiovascular Board - Standing item on Board Agenda Control Owner: Director of Strategic Partnerships | CVD Board Papers CVD Board Newsletter Ops Board Briefing | Quarterly Cardiac Board highlight reports to ICB. | Partial |  |  | Integration of the Cardiac Board and Network planned in 2023/24. | Development of the integrated Cardiac Board and Network in partnership with the ICS. Action Owner: Jonathan Develing Due date: Quarterly updates | Good progress being made against the 4 national pathways. Highlight reports are provided to the ICB on a quarterly basis as an assurance mechanism for the Cardiac Board. ACS pathway is progressing through the cardiology collaborative. Advancing CVD Prevention published (March 2023). Revised TOR for the Integrated Cardiac Board and Network now agreed including membership. Assurances now provided to the ICB through the Digital Transformation and Clinical Improvement Board. Reporting through CMAST clinical workstreams now established. Discussions in hand to align the CVD Prevention Group with the Population Health Board.
|  |  | C3) Single cardiology service developments - Standing item on Board Agenda Control Owner: Director of Strategic Partnerships | Executive and Operational Board oversight. Reports to the Board of Directors. | Independent Chair appointed to Cardiology Partnership Board. | Partial |  |  | Case for change, plan, resources, approach and timelines being explored. | Case for change, plan, resources, approach and timelines being explored and developed. Action Owner: Jonathan Mathews Due date: Quarterly updates | Work continuing to progress improvements on cardiology pathways. Cardiology pathway work has been aligned to feed into CMAST clinical pathway workstream. Liverpool Cardiology Partnership to be stood down and align to Joint Committees.
|  |  | C4) Broadgreen Site Committee - Reporting to Board of Directors Control Owner: Chief Operating Officer | Committee reporting to Board of Directors. |  | Partial |  |  | New arrangements for site committee to be developed and embedded. | TOR, workplan and Chairs reports to be established. Priorities to be progressed as per agreed workplan. Action Owner: Jonathan Mathews Due date: Quarterly update | LUHFT/LHCH Joint Site Committee (Broadgreen) continues to meet bi-monthly. Chairs report provided to Board. Key themes identified and workstreams are progressing, Formal review of 2024/25 priorities to be undertaken and aligned to Liverpool Trust joint Committee.
Return to Main Menu
Return to Main Menu

## Digital
Risk Theme: Digital
RISK APPETITE: OPEN - Upper tolerance limit 12
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO6: Population Health
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF9 Failure to ensure strong digital transformation and IT service resilience could erode LHCH’s position as a world-class provider of specialist care delivering services for patient needs Executive Risk Lead: Kate Warriner, Chief Digital & Information Officer Board Committee: Board of Directors Last Update: March 2024 | Causes - Lack of capacity and capability for transformational change and operational delivery - Insufficient investment in IT infrastructure - Varied appetite for transformational change within teams - Increasing sophistication and variety of malicious attacks - Integration of networks across the ICS - Increased reliance on digitised processes - Legacy infrastructure requiring modernisation - Legacy processes, delivery and capability requiring modernisation Consequences - Clinical innovation hindered or poorly implemented - Negative reputational impact - Loss of leading position as provider of specialist services - Disruption to services - Loss of data - ICO fines - Fraud/ theft | 4 x 3 = 12 | C1) Delivery of Digital Excellence Strategy Control Owner: Chief Digital and Information Officer | Digtal Strategy programme delivery reported to Digital Excellence Committee. Statement of Planned Benefits regulary reviewed at Digital Excellence Committee. | NHSE oversight on programme delivery. Strategic links into ICS. HIMSS 7 Accreditation. | Acceptable | 4 x 2 = 8 | YES | Delivery and realisation of planned benefits. | Digital Excellence Committee to ensure delivery of programme to timescales and planned benefits realised. Action Owner: Chief Digital and Information Officer Due date: Quarterly update | Statement of planned benefits tracked at Digital Excellence Committee. A number of benefits are being realised which are reported to the DEC through the programme highlight report. Full deep dive in progress. IDigital Business case benefits realisation to be reported to Board, April 2024. | 4 x 3 = 12 | Q4 2021/22
|  |  | C2) IDigital Service delivery Control Owner: Chief Digital and Information Officer | Partnership Board. SLA and Partnership Agreement. Audit Committee reporting bi-annual. Board reporting. Operational Board reporitng. | ISD Level 3 accreditation. | Acceptable |  |  | Retention and talent management. | Retention action plan to be developed alongside a talent management strategy. Action Owner: Chief Digital and Information Officer Due date: Quarterly update | Actions in relation to retention and talent management in place. Staff turnover is within Trust target.
|  |  | C3) Cyber security Control Owner: Chief Digital and Information Officer | Cyber Management Reports to Audit Committee DSPT Submission The Trust has implemented systems to respond to and action NHS Digitals cyber alerts (Care Certs) DEC reporting. | Internal Audit reports Cyber Essentials Accreditation | Acceptable |  |  | Cyber essentials Plus | Achievement of cyber essential plus external accreditation Action Owner: Chief Digital and Information Officer Due date: Quarterly Update | Cyber controls remain in place. Progress continues with regards to cyber priorities and defences. Cyber capacity and capability further developing including additional senior leadership and cyber apprentice in post.
|  |  | C4) Data analytics and BI Control Owner: Chief Digital and Information Officer | DEC reporting. |  | Acceptable |  |  | Delivery of the data analytics and BI development priorities. | Delivery of Data analytics and BI priorities. Action Owner: Chief Digital and Information Officer Due date: Quarterly Update | Data analytics and BI plan approved by DEC with regular highlight reporting. Good progress continues to be made with the implementation of a range of priority dashboards through the Power BI platform.
Return to Main Menu
Return to Main Menu

## Reference page
Board Assurance Framework 2022/23
i) The BAF is presented thematically to show the different types of strategic risk that have been identified by the Board in relation to the delivery of the Trust's Strategic Plan
ii) A quarterly report on progress of the strategic objectives is provided separately to the Board
iii) The Board's risk appetite in relation to each risk theme is noted - this is based upon the Board's defined apppetite for risk as set out in the Risk Management Policy
iv) Each risk is assigned an inherent risk score to estimate the uncontrolled risk - when compared with the residual (current) score it allows the Board to understand how effective the risk response is
v) Each risk is also allocated a target risk score which indicates the expected level of risk by the end of the 2021/22 - this must be below the upper tolerance limit set for the risk theme and be forecast based on
planned actions
5x5 risk scoring matrix:
• Refer to BAF Policy for operating guidance, roles and responsibilities and reporting template
Risk Appetite Levels