## Front Page
Return to Main Menu
Return to Main Menu
Board Assurance Framework
2024 - 25

## Quality & Patient Experience
Risk Theme: Quality & Patient Experience
RISK APPETITE: MINIMALIST - Upper tolerance limit 6
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO6: Population Health
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF1 Failure to maintain safety and quality and avoid harm would result in poorer patient & family experience Executive Risk Lead: Joan Mathews, Director of Nursing and Quality Board Committee: Quality Committee Last Update: January 2025 | Causes - Covid part of the long-term operating context - Population health needs change due to long-term effects of Covid - Further surges / new variants - Insufficient workforce capacity - Staff wellbeing - Nosocomial outbreaks - Patients may present more clinically unwell due to longer waiting times - A higher proportion of patients with psychological/mental health issues post covid Consequences - Poorer patient experience - Less favourable patient outcomes - Ability to maintain CQC ‘outstanding’ - Patients not treated promptly and within waiting time targets - Deterioration in positive feedback from patients and families and negative patient survey results - Failure to implement the principles from the national safety strategy | 5 x 4 = 20 | C1) The quality and safety strategy 2021-24 sets out the workstreams to ensure the hospital delivers high quality and safe care. Control Owner: Joan Mathews, Director of Nursing and Quality | IPC BAF Quarterly reports and incident reports to the Board of Directors. Quality strategy progress reports to Quality Committee and Board of Directors. Quality dashboard to Qualtiy Committee and KPIs to Board of Directors. Learning from external reviews. QI plan updates to Operational Board. PSIRF implementation plan and updates to Quality Committee. GIRFT updates to Operational Board. In-phase implementation updates to Operational Board via Risk Management Committee. | National inpatient survey results. Healthwatch reports. Internal audit reviews. NHS Staff survey results | Substantial | 3 x 2 = 6 | YES | Refresh Q&S Strategy. | To refresh the Quality and Strategy in 2024/25. Action Owner: Joan Mathews, Director of Nursing and Quality Due date: Quarterly updates | Quality priorities agreed for 2024/25. Work on full quality strategy refresh to commence. | 3 x 2 = 6 | Achieved
|  |  | C2) Infection Prevention and Control. Control Owner: Manoj Kuduvalli, Medical Director | IPC reports (including BAF) to the Board of Directors. Water and ventilation safety, antimicrobial stewardship, sepsis, and SSI committees reporting to Infection Prevention Committee to QSEC and Qualtiy Committee. Quality dashboard. | CQC reports and rating | Substantial |  |  | Further work being undertaken regarding Surgical Site Infections (SSIs). Improvements being made for sepsis screening. | Ongoing monitoring of SSIs. Continued improvement in sepsis screening. Action owner: Manoj Kuduvalli, Medical Director Due Date: Quarterly updates | Detailed risk adjusted data fed back to clinicians and digital dashboard being developed for ongoing use.
|  |  | C3) EECS and CQC mock inspections process. Control Owner: Joan Mathews, Director of Nursing and Quality | IICC report 6/12 and complaints reports annually. EECS and internal CQC mock assessments reported to Board. | Commissioner reviews of quality (quarterly) | Substantial |  |  | Alignment to new CQC assessment framework. | To align EECS and CQC mock assessments to new CQC assessment framework. Action Owner: Joan Mathews Due date: Quarterly updates | Update to EECS assessment process progressing to reflect new CQC assessment framework with a plan to cover all areas in 2024/25.
|  |  | C4)The organisational learning plan for the Trust supports improvements in practice and care for patients. Control Owner: Ben Vinter, Director of Risk and Corporate Governance | Organisation learning reported through various forums including Operational Board and via QSEC to Quality Committee. Board of Directors receives ICCI reports and learning from deaths updates (quarterly). Organisational learning strategy approved by Board through CGM. PSIRF policy and reporting. GIRFT reports and associated action plans. |  | Substantial |  |  | Failure to collate and triangulate learning from incidents could impact on patient safety and quality. | Continue to develop and maximise the use of the learning database. Learning is cascaded regularly through learning forums and comms Action Owner: Ben Vinter, Director of Risk and Corporate Governance Due Date: Quarterly updates | The organisational learning database has been rolled out for mortality, and the Trust's Patient Safety Lead is working with clinicians to raise awareness and use of the database. Wider use of the database to be revisited.
|  |  | C5) Quality Governance Structure - QSEC, and Quality Committee. Control Owner: Joan Mathews, Director of Nursing and Quality | QIA process for CIP reporting through Quality Committee. Quality dashboard reporting through Quality Committee and KPIs to Board. Annual review of Committee effectiveness. Clinical policies and guidelines approved through governance structure. Quality Committee BAF key issues report. National and local audits reported through CAEG. | CQC Insight report to Board of Directors twice yearly. | Substantial |  |  | CQC are revising their strategy therefore there may be changes to their inspection criteria. | Keep abreast of changes to the CQC strategy and embed into the trusts EECS process as required. Action owner: Joan Mathews, Director of Nursing and Quality Due Date: Quarterly updates Progress External Well led self assessment at Board's direction. Action owner: Ben Vinter, Director of Risk and Corporate Governance Due Date: Q3 | Updates to EECS progressing to reflect new CQC assessment framework as reflected above. Work planned to map well led self assessment to new CQC assessment process and engage at all levels.
|  |  | C6) Review of deaths Control Owner: Manoj Kuduvalli. Medical Director | Mortality improvement group reporting through the Quality Committee. Medical examiners. Mortality review group. | Dr Foster benchmarking | Substantial
|  |  | C7) Implementation of Clinical Strategy Control Owner: Manoj Kuduvalli, Medical Director | Draft LHCH Clinical Strategy in place. |  | Moderate |  |  | System clinical strategy. | The LHCH clinical strategy will need to be reviewed to ensure alignment to system strategy once developed. Action owner: Manoj Kuduvalli, Medical Director Due Date: Quarterly updates | Awaiting system clinical strategy. Clinical strategy priorities clearly articulated as part of the LHCH strategy refresh. Increased emphasis on system and collaborative working on future strategic direction.
Return to Main Menu
Return to Main Menu

## Operational Effectiveness
Risk Theme: Operational Effectiveness
RISK APPETITE: CAUTIOUS - Upper tolerance limit 9
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO6: Population Health
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF2 Inability to deliver annual planning activity and performance targets could result in poorer patient outcomes, inability to address the backlog of patients waiting and result in financial consequences to the Trust. Executive Risk Lead: Jonathan Mathews, Chief Operating Officer Board Committee: Integrated Performance Committee Last Update: January 2025 | Causes - Insufficient capacity to deliver expected levels of activity - Gaps in workforce - Impact of industrial action - Unmet demand that did not present / get referred to services during the height of the pandemic, leading to a significant increase in the waiting list, above core funded capacity - Further surges / new variants - Backlog patients’ conditions have worsened while waiting - Pressures of mutual aid requirement based on system priorities Consequences - Inability to meet statutory waiting list / access targets - Failing to acheive SOF level 1 - Poorer patient outcomes and experience with extending waiting times - Poor reputational consequences from elongated waiting times - Regulatory challenges | 4 x 5 = 20 | C1) Annual plan with clear activity trajectories. Control Owner: Jonathan Mathews, Chief Operating Officer | Formal monthly reporting to the Board of Directors and IPC on activity against plan. Recovery plans and trajectory signed off and in place | North West performance report overseen by ICS. | Acceptable | 4 x 3 = 12 | NO | The Trust is not recurrently resourced to deliver levels of activity. Capacity and estates to deliver increased activity. Plans are based on full utilisation of current workforce and thus workforce resilience, recruitment contraints and retention are potentially gaps in delivery. | Trust and Divisional plans to be developed as part of annual planning. Action Owner: Jonathan Mathews, Chief Operating Officer Due date: Quarterly update | Strong performance against regional and national targets. Ongoing challenges for surgical long waiters and cancer diagnostics with action plans in place to progress. Annual plannig for 25/26 started in November, subject to natiional guidance. | 3 x 3 = 9 | 2025-03-31
|  |  | C2) Formal governance structure with clear roles and responsibilities in the Divisions through to Operational Board. Control Owner: Jonathan Mathews, Chief Operating Officer | Operational Board reporting. IPC reporting. |  | Acceptable
|  |  | C3) KPIs and performance trajectories Control Owner: Jonathan Mathews, Chief Operating Officer | LHCH dashboard reviewed weekly through Performance meeting and Executive Committee. Monthly SOF report to Board and Operational Board. IPC reports. Safe Waiting List Management Group reporting to Operational Board. | Contract review meetings. MIAA report to Audit Commtitee. | Moderate |  |  | Unmet demand as a consequence of waiting list growth. Unknown requirements of systemwide mutual aid. Safe waiting list management assurances. | Safer waiting list management actions to be delivered (including SWL Group, and MIAA report recommendations). System Perofmance and Recovery Group planning actions Action Owner: Jonathan Mathews, Chief Operating Officer Due date: Quarterly updates | Waiting lists continue to be clinically prioritised for long waiters and urgent patients. Interdependencies of digital projects being reviewed. Quarterly updates to Operational Board. Significant risk identified as part of EPRO implementation, mitigating actions progressing and learning to be picked up through PSIRF process.
BAF3 Inability to achieve the five year capital programme within a challenging and uncertain operating environment and deliver an Estates Strategy that supports the provision of outstanding services Executive Risk Lead: James Thomson, Chief Finance Officer Board Committee: Integrated Performance Committee Last Update: January 2025 | Causes - Implications of ICS capital envelope with undetermined ICB estates strategy and capital prioritisation process - Ageing estate and challenging backlog maintenance risks - Cath lab major capital scheme in its final year with contingency financial risk Consequences - Impact on delivery of LHCH capital plan - Inability to invest in innovations not currently identified in the Trust’s five year financial plan - Having to re-prioritise the programme if an unidentified need arises - Disruption to operational services during a complex capital programme | 4 x 3 = 12 | C1) Robust governance in place to provide assurance on the capital programme, documented through Capital Management Group to Operational Board. Control Owner: James Thomson, Chief Finance Officer | Operational Board reporting to Board of Directors monthly. |  | Substantial | 4 x 3 = 12 | NO | Uncertainty of the ICS approach to capital, estates strategy and capital prioritisation process. | Clarity required on the impact of systemwide capital envelopes for future years Action Owner: James Thomson, Chief Finance Officer Due date: Quarterly updates | Early notification received of initial 2024/25 allocation and discussions continue with ICB. | 3 x 3 = 9 | 2025-03-01
|  |  | C2) Partnership / resilience with Propcare to deliver major schemes managed through Capital Programme Board. Control Owner: James Thomson, Chief Finance Officer | Formal monthly report to the Operational Board and bi-monthly to the Board of Directors. |  | Substantial
|  |  | C3) Formal process in place for capital planning and prioritisation including the impact of system wide capital envelopes. Control Owner: James Thomson, Chief Finance Officer | Quarterly update to the Integrated Performance Committee, monthly capital updates to the Board of Directors. Estates Strategy approved. Report to Board June 24 |  | Substantial |  |  | Exploring opportunities for contingency and system capital funding, | Continue to seek assurance on revenue position and eligibility for additional capital to support Trust priorities. Action Owner: James Thomson, Chief Finance Officer Due date: Quarterly updates | Early notification received of initial 2024/25 allocation and discussions continue with ICB.
|  |  | C4) Estates strategy in place, including inspection and maintenance programme appropriate for age and condition of infrastructure. Control Owner: Jonathan Mathews, Chief Operating Officer | 6 monthly estates strategy update to BoD. Health and Safety Committee reports to Risk Management Committee and in turm to Operational Board. Quarterly capital updates to IPC and monthly capital updates to the Board of Directors. Prioritsation execise based on gap in capital funding allocation. | Six Facet Survey. Regulatory and statutory assurance received ad hoc (e.g. fire safety, H&S etc). Broadgreen site committee reporting. CMAST Leadership Board CiC reporting to Board. | Substantial |  |  | Alignment and development of system estates strategy, emerging approach to capital, and aligned system clinical strategy. | To continue to work closely with the system to understand the developing approach to estates, capital and site. Action Owner: James Thomson, Chief Finance Officer Due date: Quarterly updates
Return to Main Menu
Return to Main Menu

## Workforce
Risk Theme: Workforce
RISK APPETITE: SEEK - Upper tolerance limit 12
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO2: Advancing Quality & Innovation, SO4: Developing People
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF4 Challenges in recruiting, developing, retaining and ensuring the wellbeing of a high quality, diverse and inclusive workforce would affect our ability to deliver world class care Executive Risk Lead: Jane Royds, Chief People Officer Board Committee: People Committee Last Update: December 2024 | Causes - Perceptions of the NHS as a place to work post Covid - Competition for talent - Expectations of Millennials entering the labour pool - Exodus from NHS of patient facing staff - Poor staff morale - Staff burn-out - Increase in mental health issues - Staff burn-out - Industrial action - Pay dissatisfaction - pay increments and cost of living -Liverpool Adult Acute & Specialist Providers (LAASP) Collaboration and the transitions into a hospital group model Consequences - A deterioration in the physical and mental wellbeing of our workforce - Loss of goodwill and staff engagement - Fluctuating capacity - Increase in long-term sickness - Increased staff turnover - Staff vacancy gaps exacerbated - Increased bank/temp staff hours - Erosion of world-class specialist talent - Lack of leadership stability - Erosion of skills and knowledge - Delays in onboarding - Reduced staff engagement - the Liverpool Adult Acute & Specialist Providers (LAASP) and the transition into a group hospital model could introduce uncertainty that could negatively impact staff engagement including job roles, structures and locations. This could result in decreased morale and reluctance to fully engage with the organisations long term strategy and short terms plans | 4 x 5 = 20 | C1) People Strategy delivery Control Owner: Jane Royds, Chief People Officer | Quarterly reports to People Committee. Bi-annual reports to the Board. | Staff survey results. MIAA audits. | Substantial | 4 x 3 = 12 | YES | Managing the unknown consequences of the collobration and the transition into the group model |  | Action Plan developed to deliver Year 3 of the People Strategy. Refresh of the People Srategy to be undertaken in 2025 which consider the national and local landscape. Use data and inteligence from the Staff Survey to support development. Continued open and transparent communication and engagement with staff will remain paramout. | 4 x 3 = 12 | Achieved
|  |  | C2) Recruitment and Retention Strategy delivery Control Owner: Jane Royds, Chief People Officer | Reports to People Delivery group and to the Recruitment and Heads of Nursing working group. Monthly Board reports on Nurse Staffing. Retention group reports to People Committee. | Staff survey results. Turnover KPI. OH data and Model Hospital data. | Moderate |  |  | There is a workforce risk in key recruitment and retention of some professional groups (e.g. Admin). Uncertainty regarding impact of system workforce controls on vacancy and headcount. | Continue to work closely with the ICB to ensure alignment of Trust annual plans, and vacancy controls and headcount. Action Owner: Jane Royds, Chief People Officer Due date: Quarterly updates | Annual workforce planning has started - Trust and divisional workforce plans for be developed as part of the cycle.
|  |  | C3) Culture and Wellbeing strategy Control Owner: Jane Royds, Chief People Officer | Quarterly report to People Committee on People Action plan progress and appointment of a Wellbeing Guardian for the Trust. Health and wellbeing Group. Improving People Practice bi-annual report to People Committee and annual to Board. | Staff survey results. NHS benchmarking on absence and turnover data. | Substantial |  |  | Continued focus on culture and staff wellbeing. | Delivery of the Culture and Wellbeing action plan. Action Owner:Jane Royds, Chief People Officer Due date: Quarterly update | Culture and Wellbeing Strategy has been approved by Board and launched with an operational action plan. 2023 staff survey results received with LHCH rated top in the country. LHCH continue to grow its Live Well, Work Work Health and Wellbeing events in collaboration with Strategic Partnerships and as part of the Broadgreen Collaborative.
[10 empty] | Collaboration on occupational health is being progressed with Alder Hey and the contract with Merseycare on psychological support has been extended. Action Owner: Jane Royds, Chief People Officer Due date: Quarterly updates | Joint OH Tender Process has commenced. A 6- months extention to our current OH provision has been agreed to ensure continuity of service. Tender presentations took place w/c 4th November 25 - contract to be awarded at the end of November.
|  |  | C4) Equality, Diversity, Inclusion and Belong Strategy delivery Control Owner: Jane Royds, Chief People Officer | Reports to Equality and Inclusion steering group and quarterly reporting to People Committee Retention Group updates. Recruitment and Retention Strategy EDIB Strategy Workforce dashboard and KPIs EDI dashboard reported to People Committee | National reporting on diversity data and information from Model Hospital for benchmarking Staff survey results on WRES and DES. | Moderate |  |  | Delivery EDIB Y2 action plan and NHS EDI improvement plan. Anti racist framework plan (although not mandated). | Deliver the EDIB Y2 action plan and Anti Racist Framework Bronze level. Action Owner: Jane Royds, Chief People Officer Due date: Quarterly updates | Staff Networks developed and several launched. LHCH Anti Racism Commitment Statement was relaunched in May 24. Anti Racism Campaign launched in October following engagement with the EDIB steering group and People Delivery Group.
|  |  | C5) Learning and Development Strategy delivery Control Owner: Jane Royds, Chief People Officer | Quarterly report to People Committee on People Action plan progress. | CQC inspection and MIAA audits. Staff survey results. | Moderate |  |  | Delivery of L&D Strategy including Scope for Growth. | Deliver the L&D strategy action plan including Scope of Growth. Action Owner: Jane Royds, Interim Chief People Officer Due date: Quarterly updates | Training Needs Analysis will be developed from the 2024 Appraisal window to inform the L&D offer (December 25)
|  |  | C6) Workforce Planning Control Owner: Jane Royds, Chief People Officer | Annual Plan approved. | Annual plan submitted to ICS. | Moderate |  |  |  | To submit workforce plan Action Owner: Jane Royds, Chief People Officer Due date: Quarterly updates | Workforce Plan has been submitted which profiles no grwoth in the workforce. People and Activity Group in place to monitor vacancies. Currently the only Trust in C&M planning on the no growth assumption required by the ICB.
|  |  | C7) Leadership and Succession Planning Control Owner: Jane Royds, Chief People Officer | Annual Executive and NED succession plans reported to respective Remuneration Committees. |  | Moderate |  |  | Comprehensive Board succession plan. | To ensure development of a comprehensive Board succession plan. Action Owner: Jane Royds, Chief People Officer Due date: Quarterly updates | Board recrutiment has resulted in full establishment with all Directors to be in post by June 2024. Board Apprisals complete. succession plans to be developed.
Return to Main Menu
Return to Main Menu
Return to Main Menu
Return to Main Menu

## Finance
Risk Theme: Finance
RISK APPETITE: OPEN - Upper tolerance limit 12
LINKS TO STRATEGIC OBJECTIVES: | SO3: Increasing value
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF5 Failure to deliver financial plans and changes in the funding regime and commissioning landscape could impact sustainability for the Trust and system partners Executive Risk Lead: James Thomson, Chief Finance Officer Board Committee: Integrated Performance Committee Last Update: November 2024 | Causes - system financial control total and duty to collaborate system financial sustainability - Changes to the commissioning landscape and regime - Increased costs associated with post pandemic recovery - Slow-down in commercial income - Ability to increase productivity, and drive out further efficiencies while managing recovery Consequences - Ability to fund strategic plans - Ability to meet financial target | 4 x 3 = 12 | C1) Finance Strategy Control Owner: James Thomson, Chief Finance Officer | Financial Plan Board Report | System Financial Plan ICB submissions | Substantial | 4 x 3 = 12 | YES | System approach to management of financial risk and allocation of resources | Focus on underlying position, and engagement with system finance leadership. Action Owner: James Thomson, Chief Finance Officer Due date: Quarterly updates | Continued collaborative working with ICS and partners around C&M position, and strong engagement from LHCH including draft surplus plan for 2024/25. | 4 x 3 = 12 | Achieved
|  |  | C2) Annual Budget and systems of budgetary control Control Owner: James Thomson, Chief Finance Officer | Financial Plan (approved) Finance Report to BoD Board of Directors/IPC Bi-mthly/Qtrly IPC and FPG | Financial Plan ICB submissions Internal Audit Plan (Annual) | Substantial |  |  | Uncertainty of impact of emerging system expenditure controls, expectations and productivity ask on local plans, budget pressures and investments. | Continue to work with the ICB and C&M CFOs to understand and manage the implications. Action Owner: James Thomson, Chief Finance Officer Due date: Quarterly updates | Ongoing discussions with the ICB and C&M CFOs.
|  |  | C3) CIP Plan Control Owner: James Thomson, Chief Finance Officer | CIP Tracker IPC & FPG April & Mthly | Financial Plan NHSE Template | Substantial |  |  | Under-developed CIP Plan, underpinned by productivy expectations. | Development of 24/25 CIP plan & tracking of schemes against target. Action Owner: James Thomson, Chief Finance Officer Due date: Quarterly updates
|  |  | C4) Commissioning arrangements Control Owner: James Thomson, Chief Finance Officer | IPC & FPG | Contract negotiations | Moderate |  |  | Transition of specialised commissioning to ICBs. | To ensure ongoing discussions and negotiations, underpinned with knowledge of complexity of specialised services as the commissioning arrangements transition to the ICB. Action Owner: James Thomson, Chief Finance Officer Due date: Quarterly updates | Regular contract meetings, information sharing and discussions ongoing. Continuing to share knowledge and understanding of specialised services. Monitoring of activity changes, demand, acuity and referral patterns to support contract discussions and ensure these are reflected in the baseline.
Return to Main Menu
Return to Main Menu

## Innovation
Risk Theme: Innovation
RISK APPETITE: SEEK - Upper tolerance limit 16
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO2: Advancing Quality & Innovation, SO3: Increasing Value
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF6 Inability to delivery the Research and Innovation agenda to exploit future opportunities Executive Lead - Manoj Kuduvalli/ Dr Jay Wright (Research) and Tom Pharaoh (innovation) Board Committee: Strategic Research & Innovation Last Update: November 2024 | Causes - Turnover of research nurses - Reduced funding for R&D - Capacity for data analytics - Capacity of leadership for Innovation strategy Consequences - Ability to maintain R&D function - Aligment of Innovation | 3 x 4 = 12 | C1) Research Strategy Control Owner: Manoj Kuduvalli, Medical Director/ Jay Wright, Director of Research | Board reports Strategic R&I Committee Grant applications Recruitment targets Operational Research Committee reports through Operational Board | Collaboration with wider research Network via LHP, regional research directors forum, LCCS strategic committee and Liverpool CRF strategic committee. ICB research landscape yet to be clarified | Acceptable | 3 x 4 = 12 | YES |  | SOF metrics for R&I in development by and via Committee | Academic appointments supporting improved connectivity and leadership Refreshed strategy - target completion date 1/4/25 Research matron recruited completing MDT approach to R&I leadership Appointment to Director of Research Operations position | 3 x 4 = 12 | Achieved
|  |  | C2) Team structure, SOPs and expertise Control Owner: Jay Wright, Director of Research | Grant applications Recruitment targets Operational Research Committee reports through Operational Board Governance team restructure | MHRA Audit reports, MIAA review, CRF operational and governance boards | Acceptable
|  |  | C3) CRN Arrangements Control Owner: Jay Wright, Director of Research | Monthly meeting with CRN. Trials Management System. | Merger of NWC and CM LCRNs will provide new structure and KPIs next year | Moderate |  |  | Uncertainty regarding funding and income streams. | Understand and influence CRN funding. Contingency actions to secure grants and commercial funding. Action Owner : Jay Wright Due date: Quarterly updates | On target for recruitment to portfolio studies. Ongoing discussions with CRN. Prioritsation of grant applications via LCCS review and internal LHCH investigator leadership of grant applications.
|  |  | C4) CRF Arrangements Control Owner: Jay Wright, Director of Research | Updates through Operational Board. | CRF Board | Acceptable
|  |  | C5) Work to establish a coordinated Trust approach to innovation Control Owner : Tom Pharaoh, Director of Strategy | Strategic R&I Committee Operational Board Board of Directors |  | Moderate |  |  | Coordinated Trust approach to innovation not yet fully established | Develop a proposal for a clear and coordinated trust approach to innovation Action Owner: Tom Pharaoh Due Date: Quarterly updates | Draft innovation strategy (developed in 2023/24) has been reviewed. Not suitable for publication. Position paper presented to Strategic Research and Innovation Committee in July 2024. Paper reviewed Trust position on innovation and outlineda potential approach to fostering innovation and developing a coordinated programme to support. Work with Executive colleagues underway to engage with partners (e.g. Health Innovation NW Coast) to further develop approach. Alignment with emerging work of LAASP R&I programmes and future UHLG R&I strategies essential. Board of Directors update scheduled for March 2025.
BAF7 Failure to be recognised as an Anchor Institution, demonstrating social value, sustainable green strategy and contribution to tackling health inequalities may increase costs in the longer term and disappoint public, staff and regulatory expectations Executive Risk Lead: Tom Pharaoh, Director of Strategy Board Committee: Board of Directors Last Update: November 2024 | Causes - Considered part of the Broadgreen site not just that of LHCH - Energy consumption not known at a local level (area by area) - Up-front investment required - Benefits poorly understood - With competing priorities and other risks, the NHS commitment to net zero may not be seen as a high priority for investment Consequences - Reputation as a responsible healthcare provider - Failure to reduce waste and realise efficiencies - Disappointment of staff engaged with Green issues - Failure to contribute toward improving air quality - declared by the LA as a climate emergency | 2 x 4 = 8 | C1) Trust's Green Plan Control Owner: Tom Pharaoh, Director of Strategy | Publication of the Trust Green Plan Interdependencies between Green Plan and Capital Program understood Year end review to BOD Mid Year report of benefit realisation to BoD. Anchor institute reports to Board. | Completion of NHSE Template OKTA (quarterly submission) Trust submitted Green Plan to ICS Cheshire and Merseyside Green Plan alignment | Moderate | 2 x 3 = 6 | YES | Potential to further develop sustainability programme and reduce environmental impact | Set out further development of a clear sustainability programme through a refreshed Green Plan (in line with national/local expectations) Action Owner: Tom Pharaoh Due Date: 30/06/2024 | To be developed through Health Inequalities and Anchor Institution Group | 2 x 2 = 4 | 2025-04-01
|  |  | C2) Social Value Accreditation Control Owner: Tom Pharaoh, Director of Strategy | Exec Group and Ops Board oversight. CEO Report to Board of Directors. Anchor institute reports to Board. | Social Value accrediation through ICS (Level 1) | Substantial |  |  | Potential to further develop Trust's wider health inequalities work programme following historical focus on anchor institution activities | Develop balanced health inequalities and anchor institution work plan for 2025/26 Action Owner: Tom Pharaoh Due Date: 31/03/2025 | To be developed through new Health Inequalities and Anchor Institution Group. Original action delayed by lack of programme management resource to support.
|  |  | C3) Prevention Pledge Control Owner: Tom Pharaoh, Director of Strategy | Exec Group and Ops Board oversight. CEO Report to Board of Directors. Annual prevention plan report to Board of Directors. Anchor institutes report to Board. | ICS Health Equalities Group Quarterly return to ICB | Substantial |  |  | Additional clarity needed on governance of health inequalities and anchor institution programme and programme management approach | Review Health Inequalities and Anchor Institution Group constitution and programme management arrangements Action Owner: Tom Pharaoh Due Date: 28/02/2025 | Group established in October 2024. Constitution of Group reviewed in January 2025 to ensure effectiveness. Programme management arrangements to be clarified through ongoing review of team structures within Strategy and Transformation Division (proposal expected January 2024).
|  |  | C4) Wider Health Inequalities workstream Control Owner: Tom Pharaoh, Director of Strategy | Reporting to Board of Directors | ICS Health Equalities Group | Moderate |  |  | Additional clarity needed on reporting and Board assurance arrangements | To establish assurance reporting of health inequalities work within the Trust. Action Owner: Tom Pharaoh Due Date: 6-monthly updates | Action complete - to migrate to controls for next report. LHCH position and proposed approach to health inequalities, including reporting and assurance, set out in paper to Board of Directors in September 2024. 6-monthly updates to Board agreed. Next report March 2025. in addition Health Inequalities and Anchor Institution Group chair's report to go to Operational Board after each meeting.
Return to Main Menu
Return to Main Menu

## System Working
Risk Theme: System Working and Collaboration
RISK APPETITE: SEEK - Upper tolerance limit 16
LINKS TO STRATEGIC OBJECTIVES: | SO2: Advancing Quality & Innovation, SO5: Leading through Collaboration, SO6: Population Health
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF8 System working and provider landscape changes may present challenges in ensuring heart and lung care is led and optimised in the best way for patients through Liverpool and with priorities aligned to system partners across Cheshire & Merseyside and beyond. Executive Risk Lead: Tom Pharaoh, Director of Strategy Board Committee: Board of Directors Last Update: November 2024 | Causes - Maturity of the ICS and Place - Further development of city collaboratiion - Changes in commissioning expectation - Unclear clinical priorities - Newly emerging system strategy/ plans - Organisational sovereignty and/or autonomy Consequences - Conflicting priorities between LHCH, City and ICS - Diversion of LHCH leadership capacity - Loss of autonomy - Clinical disengagement and/or disrupted focus - Disruption to established clinical networks | 4 x 5 = 20 | C1) Liverpool Adult Acute and Specialist Providers governance (LAASP) Control Owner: Ben Vinter, Director of Risk and Corporate Governance / Tom Pharaoh, Director of Strategy | Chief Executive reports to BOD Trust participation in LAASP Programme Board Joint Committee TORs to be considered and approved by Board. | Regular reporting from Liverpool Trust Joint Committee. | Moderate | 4x4 =16 | YES | Uncertainty regarding delegation and and pace and areas of decision making. | Continued particpation in LAASP forums to shape and influence work. Ensure the Trust has appropriate representation at the ICS, CMAST, Provider collaboratives, specialised commissioning and local place based (e.g. One Liverpool) governance forums. Action Owner: Tom Pharaoh Due date: Quarterly updates | LHCH representation and engagement continues across a range of forums. LHCH continues to play an active role in the system. LHCH Executive Team is engaging in programme to further build upon provider collaboration in Liverpool. Chair and CEO part of LAASP Joint Committee. 3 LHCH Execs acting as SROs in LAASP programmes. Director of Risk and Corporate Governance is SRO for LHCH integration into University Hospitals of Liverpool Group (UHLG). Two further Execs involved in LAASP Clinical Reference Group. | 4 x 3 = 12 | 2025-03-31
|  |  | C2) Active LHCH participation in effective C&M clinical forums - CVD Board and Respiratory Network Control Owner: Tom Pharaoh, Director of Strategy |  | CVD Board updates to Operational Board. National CVD Board updates through CEO report to Board of Directors. | Moderate |  |  | Establishment of single CVD board with clarified role following review of system governance arrangements | LHCH support for establishment of single system CVD Board and work programme Action Owner: Tom Pharaoh Due date: Quarterly updates | LHCH has supported the integration of cardiac system governance arrangements. LHCH clinician chairs new joint ICB and cardiac clinical network board. LHCH DoS is a member of the Board and LHCH admin services meeting. System governance now clarified (including ongoing role of Cardiology Provider Alliance and CVD prevention group) to allow focus on development and delivery of work plan. LHCH will also support and engage in CVD Prevention Group to be reformed under leadership of ICB Population Health team.
|  |  | C3) LHCH engagement in the work of the CMAST Cardiology Provider Alliance Control Owner: Tom Pharaoh, Director of Strategy |  | CMAST CiC reporting to Board. | Moderate |  |  | Key work streams remain in development on behalf of CMAST, including a cath lab strategy and options appraisal for the region | Ccontinued leadership, LHCH engagement and contribution to delivery of priorities. Action Owner: Tom Pharaoh Due date: Quarterly updates | Cardiology Provider Alliance chaired by LHCH cardiologist John Morris. Regular reporting through CMAST work streams and to LHCH Operational Board.
|  |  | C4) Broadgreen Operational Site working - Reporting to Board of Directors Control Owner: Jonathan Mathews, Chief Operating Officer | Reporting to Board of Directors. | Consideration by LAASP JC as required | Moderate |  |  | Priorities to be agreed and delivered. | Priorities to be progressed as per agreed work plan. Action Owner: Jonathan Mathews Due date: Quarterly update | LUHFT/LHCH Joint Site Committee stood down in line with establishment of LAASP work. Broadgreen operational site discussions continue and will report to Board through executive committee. Key themes identified and work streams to be revisited and reviewed. Formal review of 2024/25 priorities and agreed scope and accountability to be progressed through LAASP Programme Board
|  |  | C5) System governance and representation Control Owner: Ben Vinter, Director of Risk and Corporate Governance / Tom Pharaoh, Director of Strategy | Chief Executive reports to BOD Papers on Code of Governance compliance, provider licence and addendum for Governors. Committee in Common and Joint Committee TORs approved by Board. | Regular reporting from CMAST CiC and Liverpool Trust Joint Committee. | Substantial |  |  | Uncertainty regarding delegation and decision making. | Ensure the Trust has appropriate representation at the ICS, CMAST, Provider collaboratives, specialised commissioning and local place based (e.g. One Liverpool) governance forums. Action Owner: Ben Vinter / Tom Pharaoh Due date: Quarterly updates | Represenation in all appopriate local, ICS and regonal forums coninutes
Return to Main Menu
Return to Main Menu
Return to Main Menu
Return to Main Menu

## Digital
Risk Theme: Digital
RISK APPETITE: OPEN - Upper tolerance limit 12
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO6: Population Health
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF9 Failure to ensure strong digital transformation and IT service resilience could erode LHCH’s position as a world-class provider of specialist care delivering services for patient needs Executive Risk Lead: Sarah Barr, Chief Digital & Information Officer Board Committee: Board of Directors Last Update: November 2024 | Causes - Lack of capacity and capability for transformational change and operational delivery - Insufficient investment in IT infrastructure - Varied appetite for transformational change within teams - Increasing sophistication and variety of malicious attacks - Integration of networks across the ICS - Increased reliance on digitised processes - Legacy infrastructure requiring modernisation - Legacy processes, delivery and capability requiring modernisation Consequences - Clinical innovation hindered or poorly implemented - Negative reputational impact - Loss of leading position as provider of specialist services - Disruption to services - Loss of data - ICO fines - Fraud/ theft | 4 x 3 = 12 | C1) Delivery of Digital Excellence Strategy Control Owner: Sarah Barr, Chief Digital and Information Officer | Digtal Strategy programme delivery reported to Digital Excellence Committee. Statement of Planned Benefits regulary reviewed at Digital Excellence Committee and reported to Board. | NHSE oversight on programme delivery. Strategic links into ICS. HIMSS 7 Accreditation. | Substantial | 4x4 =16 | NO | Delivery and realisation of planned benefits. Robust and appropriate governance for digitial . | Digital Excellence Strategy refresh in 2024/25. Refreshed iDigital Partnership Board and contractural arrangements supporting BAU governance. Action Owner: Chief Digital and Information Officer Due date: Jan 2025 |  | 4 x 3 = 12 | 2026-03-31
|  |  | C2) IDigital Service delivery Control Owner: Sarah Barr, Chief Digital and Information Officer | Partnership Board. SLA and Partnership Agreement. Audit Committee reporting bi-annual. Board reporting. Operational Board reporitng. | ISD Level 3 accreditation. | Moderate |  |  | Retention and talent management. | Retention action plan to be developed alongside a talent management strategy.To be reviwed at DEC with turnover and vacancies managed Action Owner: Chief Digital and Information Officer Due date: Quarterly update | Actions in relation to retention and talent management in place. Staff turnover is within Trust target. Further review on vacancies and turnover planned
|  |  | C3) Cyber security Control Owner: Sarah Barr, Chief Digital and Information Officer | Quaterly Cyber & IG Management Reports to Audit Committee DSPT Submission DEC reporting. CCIO Chaired | Internal Audit reports | Moderate |  |  | Cyber Essentials and Cyber Essentials Plus | Achievement of cyber essential plus external accreditation. Review of internal governance to manage Security posture. Review of Cyber resources Infrastructure review planned Increased reporting planned to Audit Commitee (Quarterly) Action Owner: Chief Digital and Information Officer Due date: Quarterly Update | Progress continues with regards to cyber priorities and defences. A review of infrastructure and planned accreditations in progress.
|  |  | C4) Data analytics and BI Control Owner: Sarah Barr, Chief Digital and Information Officer | DEC reporting. |  | Substantial |  |  | Delivery of the data analytics and BI development priorities. | Delivery of Data analytics and BI priorities. Action Owner: Chief Digital and Information Officer Due date: Quarterly Update | Data analytics and BI plan approved by DEC with regular highlight reporting. Good progress continues to be made with the implementation of a range of priority dashboards through the Power BI platform. Review of internal governance with wider Trust governance to manage prioritisation.
|  |  | C4) System digital collaboration Control Owner: Sarah Barr, Chief Digital and Information Officer | DEC reporting. Operational Board updates. Board of Directors digital excellence reports. |  | Moderate |  |  | System priorities continue to be developed. | Engagement and involvement in digital systems collaboration. Action Owner: Chief Digital and Information Officer Due date: Quarterly Update | Engagement with system CIOs continues. Discussions and aligned decision making to support Liverpool EPR developments as approved through the Board of Directors in April 2024. Along with regional technical infratructure reviews
Return to Main Menu
Return to Main Menu

## Digital Proposed
Risk Theme: Digital
RISK APPETITE: OPEN - Upper tolerance limit 12
LINKS TO STRATEGIC OBJECTIVES: | SO1: World Class Care, SO6: Population Health
Risk description & information | Causes & consequences | Inherent risk score (I x L) | Key controls | Board Assurance |  |  | Residual risk score (I x L) | Within risk tolerance? | Gaps in Control / Assurance | Actions |  | Target risk score (I x L) | Estimated date of achievement of target score
|  |  |  | Internal sources of assurance | External sources of assurance | Overall assurance level |  |  |  | Planned action | Progress update
BAF9 Failure to ensure sufficient development and adoption of digitisation across the Trust, combined with increasing cyber threats, could constrain service improvements, reduce patient benefits, and result in major security breaches that disable the Trust’s systems and lead to significant data loss. Executive Risk Lead: Sarah Barr, Chief Digital & Information Officer Board Committee: Board of Directors Last Update: January 2025 | Causes - Lack of capacity and capability for transformational change and operational delivery - Varied appetite for transformational change within teams - Unkown national funding arrangements for digital --Inconsistent and unrelaible data recording at source - Increasing sophistication and variety of malicious attacks -Integration of networks across the ICB - Increased reliance on digitised processes - Legacy infrastructure requiring modernisation -Heightened Consequences - Inability to achieve intended benefits for patient care and safety - Inability to ensure data-driven decision making -Lost opportunity to modernise - Inefficient use of resources -Unsustainable operating costs - Disruption to services - Loss of data and access to systems - ICO fines (highest maximum amount is17.5mor 4% of the annual turnover,whichever is highest - Fraud/ theft -Reputational Damage | 4 x 3 = 12 | C1) Digital Committee established with Medical Director as Senior Responsible Owner (SRO) Digital Board is the single governance for Trust wide Digital assurance. Digital Board ensures the Trust's strategic and operational plans are supported by Digital Technology. Control Owner: Sarah Barr, Chief Digital and Information Officer | The Digital Committee reports monthly with quartley Cyber and IG reporting into Audit Commitee. Digital programme plan, Business Intelligence Plans and Cyber and IG plans are reviewed through 6 weekly Digital Commitees Regular Digital reporting to Trust Board LIverrpol Acute and Specialist providers updates - Digital & Data reported through Digital commitee | NHSE oversight on programme delivery on Digital asprirants programme.(now complete) LAASP Digital and Data Workstream/Joint Committee oversight | Substantial | 4x4 =16 | NO | Delivery and realisation of planned benefits. Robust and appropriate governance for digitial services under Digital Committee. Robust Digital staffing | Review of programme portfolio and strategic ambition to be undertaken in line with LAASP Review of data and analyltics priorities Review of IG/Cyber priorities Staffing plan in place post April 25 Action Owner: Chief Digital and Information Officer Due date: April 2025 | Working group established for TUPE arrangements 1/4/25 Review of staffing requirements post April in progress | 4 x 3 = 12 | 2026-03-31
|  |  | C2) Trust Digital Strategy in place (2025) and C&M Digital and Data Startegy in place to support and align local, regional and national startegic objectives Control Owner: Sarah Barr, Chief Digital and Information Officer | Trust Digital Strategy endosrsed by Trust Board Strategic links into ICB. | Strategic alignment to ICB Digital and Data Strategy . | Moderate |  |  | Digital Strategy Post 2025 | Review of requirements in line with LAASP, C&M Digital and data startegy and National requirements Action Owner: Chief Digital and Information Officer Due date: January 2026 | Digital and Data Workstream in place for LAASP LHCH involvement in C&M Digita and Data strategy
|  |  | C3) Digital Maturity: International Digital Maturity accreditation gained via HealthCare Information Management Systems Socitey (HIMMS) Level 7 for Electronic Medical Record Adoption Mocel (EMRAM) National Digital Maturity Assessment: establishing a digital maturity baseline for 23/24 for all seven domains of the What Good Looks like Framework (WGLL) Well Led, Ensure Smart Foundations, Safe Practice, Support People, Empower Citizens, Improve care and Health Populations. 24/25 assesment submitted Skills Development Network - Level 3 accrediation- towards excellence accrediation for digital staff Control Owner: Sarah Barr, Chief Digital and Information Officer | Digital Committee reporting. Medical Director/CCIO Chaired | HIMSS 7 Accreditation. NHSE Benchmarking for National Digital Maturity assesment (DMA) North West Skills Develeopment Network Level 3 accreditation. | Substantial |  |  | Plans for renewal of accreditaions (2025/2027) | Development of DMA plans for 2025 submission Work with NW Skills Development Network for review of "Towards Excellence" Level 3 accrediation - in line with staffing changes Action Owner: Chief Digital and Information Officer Due date: July 2025 | Awaiting National Digital Maturity Assesment expected February 2025
|  |  | C4) Microsoft Defender for Endpoint (MDE) NHS England 24/7 monitoring for all enrolled devices through Cyber Security Operations Centre (CSOC) Control Owner: Sarah Barr, Chief Digital and Information Officer | Digital Committee reporting. Medical Director/CCIO Chaired Quartley Cyber and IG reporting into Audit Commitee. | NHS England Cyber Security Operations Centre reporting | Moderate |  |  | Adopoption of enhanced standards, Cyber Essentials (CE) Cyber Essentials + IS027001 Shadow IT (unknown IT developments) that could be being performed by other departments and Digital Security not made aware. | Achievement of cyber essential plus external accreditation. Review of internal governance to manage Security posture. Review of Cyber resources Infrastructure review planned Increased reporting planned to Audit Commitee (Quarterly) Action Owner: Chief Digital and Information Officer Due date: March 26 | Progress continues with regards to cyber priorities and defences. A review of infrastructure and planned accreditations in progress.
Return to Main Menu
Return to Main Menu

## Reference page
Board Assurance Framework 2022/23
i) The BAF is presented thematically to show the different types of strategic risk that have been identified by the Board in relation to the delivery of the Trust's Strategic Plan
ii) A quarterly report on progress of the strategic objectives is provided separately to the Board
iii) The Board's risk appetite in relation to each risk theme is noted - this is based upon the Board's defined apppetite for risk as set out in the Risk Management Policy
iv) Each risk is assigned an inherent risk score to estimate the uncontrolled risk - when compared with the residual (current) score it allows the Board to understand how effective the risk response is
v) Each risk is also allocated a target risk score which indicates the expected level of risk - this must be below the upper tolerance limit set for the risk theme and be forecast based on
planned actions
5x5 risk scoring matrix:
• Refer to BAF Policy for operating guidance, roles and responsibilities and reporting template
Risk Appetite Levels